KIGALI IMPLEMENTATION PLAN (KIP) FOR SIERRA LEONE

Stage I

January 2024

Table of Contents

LIST OF TABLES	ii

LIST OF FIGURES	iii

ABBREVIATIONS AND ACRONYMS	iii

PROJECT COVER SHEET	v

EXECUTIVE SUMMARY	viii

I. BACKGROUND	1

I.1	Policy/legislative/regulatory and institutional frameworks related to HFC	1

A.	Policy/legislative/regulatory framework	1

B.	Institutional framework	2

C.	RAC training framework	3

I.2	Overview of the HCFC phase-out management plan implementation	4

I.3 Implementation status of HFC-related activities	6

II. HFC CONSUMPTION BY SUBSTANCE AND SECTOR	7

II.1	Methodology and validation	7

A.	Preparatory work	7

Data Validation	10

II.2	HFC consumption data (2016- 2022)	10

A.	List of Importers	11

B.	HFC baseline	12

C.	Prices of refrigerants	13

D.	RAC service technicians	14

II.3	Sectoral distribution of HFCs	14

A.	Refrigeration servicing sector	17

B.	Air conditioning servicing sector	18

III. HFC PHASE-DOWN STRATEGY	22

III.1	Overarching strategy	22

III.2	Projections of HFC consumption, prioritization, and proposed reductions	22

III.4	Detailed KIP strategy	25

III.5	Stage I implementation programme	27

A.	Activities to be implemented under KIP Stage I	27

III.6	Relation between the Kigali HFC implementation plan and the HCFC phase-out management plan	37

III.7	Other impacts on the environment including the climate	39

III.8	Sustainability and risk assessment	39

III.9	Consideration of the Multilateral Fund gender mainstreaming policy	40

III.10	Co-financing	42

III.11	Business plan	42

IV. PROJECT COORDINATION AND MANAGEMENT	44

V. PLAN OF ACTION FOR THE FIRST TRANCHE	45

ANNEX: AGREEMENT BETWEEN THE GOVERNMENT AND THE EXERCUTIVE COMMITTEE	48

Appendix A: TEMPLATE SCHEDULE OF PHASE-DOWN COMMITMENTS AND FUNDING TRANCHES UNDER THE KIP	49

Appendix B: SCHEDULE OF PHASE-OUT COMMITMENTS AND FUNDING TRANCHES UNDER THE HPMP	50

Appendix C: SAMPLE QUESTIONNAIRE	51

# LIST OF TABLES

Table 1: The key stakeholders and their roles	2

Table 2: Overview of RAC training institutes	4

Table 3: RAC equipment sub sectors	8

Table 4: Tasks, Compositions, Roles, and Responsibilities of Personnel’s	9

Table 5: Source of Data for RAC sector	10

Table 6: Refrigerant (HFC & HCFC) consumption (2016- 2022) in metric tons (MT)	11

Table 7: CO2eq emissions for HFC refrigerants reported in 2022	11

Table 8: List of Importers of HFCs and HCFC	12

Table 9: Calculation of the HFC baseline	13

Table 10: Number of technicians working in the RAC sector	14

Table 11:  Overall stocks of RAC equipment (2022)	14

Table 12:  Distribution of HFC use in RAC sub-sectors (2022)	15

Table 13: Distribution of HFC use for RAC sub-sectors direct emission in TCO2eq. (2022)	16

Table 14: Domestic Refrigeration and Refrigerant Use	17

Table 15: Commercial Refrigeration and Refrigerant Use	17

Table 16: Industrial Refrigeration and Refrigerant Use	18

Table 17: Transport Refrigeration and Refrigerant Use	18

Table 18: Marine Refrigeration and Refrigerant Use	18

Table 19: Domestic AC and Refrigerant Use	19

Table 20: Commercial AC and Refrigerant Use	19

Table 21: Mobile AC Refrigeration and Refrigerant Use	20

Table 22:  Total HFC emissions projections under BAU Scenario	25

Table 23: Planned Stages of the KIP and potential activities	26

Table 24:  KIP Stage I Tranches and budget for proposed activities	29

Table 25: Work plan schedule for proposed activities for KIP Stage I	35

Table 26: Synergy between the HPMP Stage II and the KIP Stage I	37

Table 27: proposed activities and their potential impact to the environment	39

Table 28:  Potential risks and mitigation measurers	40

Table 29:  Gender mainstreaming	41

Table 30: Business plan	43

Table 31: First Tranche Plan of Action	45

# LIST OF FIGURES

Figure 1: Schematic representation of the Institutional arrangements	3

Figure 2: Prices of Refrigerant	13

Figure 3: Comparison of HFC use and TCO2eq emissions across sectors as of 2022	21

Figure 4: Comparison of HFC use and TCO2eq emissions as of 2022	21

Figure 5: HFC use expected to grow under BAU expected to grow under BAU	23

Figure 6: Comparison between HFC consumption under BAU and Kigali phase down Schedule	24

# ABBREVIATIONS AND ACRONYMS

| AC | Air Conditioning |
| --- | --- |
| CO2 | Carbon Dioxide |
| CO2eq | Carbon Dioxide Equivalent |
| COMREF | Commercial Refrigeration |
| DOMREF | Domestic Refrigeration |
| GDP | Gross Domestic Product |
| GoSL | Government of Sierra Leone |
| GWP | Global Warming Potential |
| HC | Hydrocarbons |
| HFC | Hydrofluorocarbon |
| HCFCs | Hydrochlorofluorocarbons |
| HPMP | Hydrochlorofluorocarbon Phase-out Management Plan |
| IMS | Information Management System |
| INDSREF | Industrial Refrigeration |
| KIP | Kigali Implementation Plan |
| Kg | Kilograms |
| NAP | National Adaptation Programme |
| NAPA | National Adaptation Programme of Action |
| NCCPF | National Climate Change Strategy and Action Plan |
| NBS | National Bureau of Statistics |
| NRA | National Revenue Authority |
| NOU | National Ozone Unit |
| MAC | Mobile Air Condition |
| MLF | Multilateral Fund |
| MT | Metric Tonnes |
| MTCO2eq. | Metric Tonnes Carbon Dioxide Equivalent |
| ODP | Ozone Depletion Potential |
| ODS | Ozone Depleting Substances |
| PMU | Project Management Unit |
| RAC | Refrigeration and Air-Conditioning |
| REF | Refrigerator |
| RSS | Refrigerator Servicing Sector |
| RRR | Recycling, Recovery, and Reclamation |
| SLFA | Sierra Leone Fisheries Authority |
| SLEC | Sierra Leone Energy Commission |
| SIT | Sierra Leone Institute of Technology |
| SLLA | Sierra Leone Licensing Authority |
| SLRC | Sierra Leone Revenue Commission |
| TRANSREF | Transport Refrigeration |
| UNIDO | United Nations Industrial Development Organization |
| UNEP | United Nations Environment Programme |
| UNFCCC | United Nations Framework Convention on Climate Change |

# PROJECT COVER SHEET

| COUNTRY NAME | SIERRA LEONE |
| --- | --- |
| LEAD IMPLEMENTING AGENCY | UNEP |
| COOPERATING IMPLEMENTING AGENCY(-IES) | UNIDO |

| COMPLETE DOCUMENTATION CHECKLIST |  |  |
| --- | --- | --- |
| DOCUMENTS SUBMITTED | Yes/No | Comments |
| Letter of transmittal | Yes |  |
| Executive summary | Yes |  |
| Kigali HFC implementation plan (KIP) stage I proposal | Yes |  |
| Independent technical review for investment projects | N/A |  |
| Draft Agreement | Yes |  |
| HFC REGULATIONS IN PLACE | Date | Comments |
| HFC licensing system (operational) | 13/09/2020 |  |
| HFC quota system (operational) |  | Anticipated to be established by 2024 and operational in 2025 |
| Other regulatory measures related to the Kigali Amendment |  |  |

| SUBMISSION OF HFC CONSUMPTION DATA REPORTS |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Data reports | Latest year reported |  | Value |  | Comments |  |
|  |  |  | MT | CO2-eq tonnes |  |  |
| Country programme (CP) | 2022 |  | 172.83 | 386,933.22 |  |  |
| Article 7 | 2022 |  | 172.83 | 386,933.22 |  |  |
| Are CP and Article 7 HFC consumption data consistent? Explain any inconsistencies in Comments |  |  |  | Yes/No |  |  |
|  |  |  |  | Yes |  |  |
| HFC PHASE-DOWN COMMITMENTS FOR THE STAGE |  |  |  |  |  |  |
| Phase-down to be achieved (%) |  | 10% | Year when phase-down will be achieved |  |  | 2029 |
|  |  |  | Value |  | Established or estimated? |  |
|  |  |  | MT | CO2-eq tonnes |  |  |
| HFC baseline |  |  |  | *351,294 | Estimated based on reported data |  |
| HFC starting point |  |  | tbc | tbc |  |  |

* The HFC baseline is calculated as the average of HFC consumption reported between the years 2020 - 2022, plus (+) 65 % of the country’s HCFC baseline.

| SECTORS INVOLVED IN HFC PHASE-DOWN |  |  |  | Yes/No |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Servicing |  |  |  | Yes |  |  |
| Manufacturing |  |  |  | No |  |  |
| MAIN COMPONENTS INCLUDED IN THE SUBMISSION |  |  |  | Yes/No |  |  |
| Overarching strategy |  |  |  | Yes |  |  |
| Strategy and action plan for stage I |  |  |  | Yes |  |  |
| Plan of action for the first tranche including planned date of completion |  |  |  | Yes |  |  |
| Co-financing |  |  |  | Yes |  |  |
| Impact on the environment |  |  |  | Yes |  |  |
| Implementation work programme and timeframe |  |  |  | Yes |  |  |
| Project coordination and management and modalities of implementation and disbursement |  |  |  | Yes |  |  |
| Consideration of the Multilateral Fund gender policy (completed checklist) |  |  |  | Yes |  |  |
| Sustainability of the HFC phase-down and assessment of risk |  |  |  | Yes |  |  |
| Energy-efficiency considerations (optional) |  |  |  | No |  |  |
| BUSINESS PLAN ALLOCATION AND FUNDING |  |  |  |  |  |
| Funding (US $) | 2024-25 | 2026-27 | 2028-30 |  | Total |
| Business plan allocation |  |  |  |  |  |
| Proposed amount | 88,500.00 | 76,300.00 | 15,200.00 |  | 180,000 |
|  |  |  |  |  | Yes/No/n.a. |
| Justification provided if KIP funding is not included in the business plan |  |  |  |  | Yes |
| Justification provided if KIP value varies from the proposed amount of funding |  |  |  |  | N/A |
| Funding consistent with HFC phase-down cost guidelines regarding the cut-off date, second stage conversions, and cost-effectiveness thresholds (indicate “n.a.” if the guidelines are not approved yet) |  |  |  |  | Yes |
| Funding for the last tranche requested in the last year of implementation |  |  |  |  | No |
| Justification provided on how the proposed funding levels can enable the fulfilment of the required disbursement threshold by the time of the next tranche request |  |  |  |  | Yes |
| Consideration of policies on individual projects in determining funding levels, i.e., transnational corporations, foreign ownership, unintentional technology upgrade, public domain technologies, incremental operating savings (e.g., alternative energy savings) |  |  |  |  | Yes |

| # EXECUTIVE SUMMARY |  |
| --- | --- |

Background

Sierra Leone adopted the Kigali Amendment, the most current modification, on 20th June, 2020, as part of its commitment to the Montreal Protocol.  The country has successfully ratified all the amendments to the Montreal Protocol.

Ongoing HCFC phase out activities

Sierra Leone’s consumption of Hydrochlorofluorocarbons (HCFCs) is in the servicing of refrigeration and air conditioning (RAC) equipment.  The HPMP Stage-I for Sierra Leone was approved at the 65th Meeting of the Executive Committee with a total funding of US$210,000 plus implementing agencies support cost for the period 2011 to 2020; to reduce consumption of HCFCs by 35% of the baseline. The established baseline consumption of HCFCs for Sierra Leone was 30 metric tons.

The Government of Sierra Leone (GoSL) had made tremendous progress on the implementation of activities under stage I of the Hydrochlorofluorocarbon Phase-out Management Plan (HPMP). The HPMP Stage-I has successfully enabled Sierra Leone to freeze HCFC baseline in 2013, and achieved 10 percent reduction in consumption of HCFC by 2015 in line with the accelerated HCFC phase-out schedule under the Protocol.

Sierra Leone had already achieved more than 35% HCFCs consumption reduction before the 2020 agreed target under the Montreal Protocol. The HPMP Stage-I has successfully phased out a total of 0.58 ODP tons of HCFCs in the country as of 2020.

Furthermore, the successful implementation of HPMP Stage-I has achieved a net direct emission reduction of 18,907 tons of carbon dioxide equivalent per year. The stage II implementing activities of the HPMP commenced in January 2023.

Status of HFC related activities

In line with Sierra Leone's efforts to combat the use of HFCs, the Kigali Amendments Enabling Activity Project was completed in 2020, helping Sierra Leone complete the Kigali ratification process in 2020. Sierra Leone also receive funding and support from external sources. The FML for the RAC sector is primarily aimed at addressing the national air conditioning sector, helping Sierra Leone transition from HCFCs to natural refrigerants.

Regulatory and institutional framework

Sierra Leone being party to the Montreal Protocol committed and aligned itself with other nations in phasing out the consumption of the controlled ODS under the Montreal Protocol phase out targets.

In this regard the National Ozone Unit (NOU) was established under the Environment Protection –Sierra Leone (EPA-SL) to coordinate the activities on the phasing out consumption of the ODS in the country.

In 2008, the Government of Sierra Leone passed an Act in Parliament for the establishment of the Environment Protection Agency (EPA) and for the protection of the environment and this 2008 EPA Act has been repeal and replaced with the EPA Act 2022. Part VII of that 2022 Act addresses ozone issues targeting banned and controlled ozone depleting substances. To accelerate the implementation of the Montreal Protocol and the EPA Act of 2008 as amended in 2010 and the new 2022 Act, the NOU developed an Ozone Depleting Substances regulation of 2010 and came into force in 2011.

The regulation of 2010 targets specifically the prohibition of the importation of refrigerators, air conditioning containing controlled substances, importation of second handed equipment containing banned or controlled substances as stipulated in the Part V of the EPA Act, 2008 and Part VII of the EPA Act, 2022, registration and certification of servicing workshops, establishment of certification scheme for technicians, establishment of an import /export licensing system etc.

In respect of the above stated regulation on controlling ODS, there is a functional quota and license system in place for HCFC. The current regulation is used to license and regulate the importation of HFC but does not allow for a quota system. However, the draft regulation which is yet to be passed into law will bring into force additional regulatory measures, including the quota system that will further limit the consumption of HFCs. The revised regulation is expected to be passed into law in 2024 and thus bring into force the quota system by early 2025.

The private sector is also regulated through the acquisition of an environmental permit from EPA-SL wherein they are expected to report on a quarterly basis ozone protection. The NOU is also obliged to undertake any assessment of the phase-out programme and encourage stakeholders to switch to ODS alternatives.

The Finance Act of 2014 requires importers and exporters to declare as required by law all products for onward inspection at all border crossing points. Similarly, the Sierra Leone Customs Acts 2011 discourage the issue of smuggling of goods in and out of the country through the institution of strictly penalty.

HFC consumption and sector distribution

Sierra Leone is dependent on refrigerant imports to meet the servicing needs of the refrigeration and air conditioning sector (RAC).

While the country has been reporting HCFC imports under the Article 7 data reporting requirement of the Montreal Protocol, HFCs have only more recently been incorporated into the overall data reporting regime and thus the has been reporting HFC imports since 2020.

| Refrigerants | GWP | Consumption (Metric Tonne) |  |  |  |  |  |  | % of Refrigerant share in 2022 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 | 2022 |  |
| R32 | 675 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 10.50 | 6.08% |
| R134a | 1,430 | 0.00 | 0.00 | 38.30 | 40.30 | 65.96 | 70.58 | 80.09 | 46.34% |
| R404A | 3,920 | 0.00 | 10.30 | 12.3 | 12.00 | 14.65 | 17.85 | 21.78 | 12.60% |
| R407A | 2,107 | 0.00 | 4.90 | 5.00 | 6.30 | 6.50 | 10.50 | 15.00 | 8.68% |
| R407C | 1,774 | 6.10 | 3.20 | 4.40 | 5.70 | 5.10 | 7.16 | 8.00 | 4.63% |
| R410A | 2,088 | 0.00 | 7.40 | 7.90 | 8.90 | 14.50 | 18.34 | 19.15 | 11.08% |
| R507A | 3,985 | 0.00 | 0.00 | 0.00 | 0.00 | 6.23 | 7.23 | 10.80 | 6.25% |
| R508B | 3,985 | 0.00 | 0.00 | 0.00 | 0.02 | 3.05 | 5.20 | 7.50 | 4.34% |
| Total |  | 6.10 | 25.80 | 67.90 | 73.22 | 115.99 | 136.86 | 172.83 | 100% |

Refrigerant (HFC) consumption (2016- 2022) in metric tons (MT)

In 2022, R134a was the dominant refrigerant consumed making up 46.34% of total HFC consumption. The other HFCs namely R508B, R407C, R32, R507A, R407A, R410A and R404A accounted for 4-13% of total HFCs. Due to significantly different GWP between refrigerants, variations in absolute quantities of specific refrigerants do not reflect a similar pattern in CO2eq emissions. For instance, R134a constitutes 46.34% of the total refrigerant used, but emits 29.60% of total CO2eq emissions.  In contrast R404A which amounts for only 12.60% of total HFC refrigerant quantities is responsible for 22.08% of the CO2eq emissions.

This is an important factor that defines the kind of strategy Sierra Leone must adopt in order to ensure that the overall CO2eq emissions are contained in order to comply with the Kigali phase down targets.

HFC baseline

Under the Kigali Amendment, Sierra Leone has been listed as an Article 5, Group 1, country with respect to the HFC phase down schedule to be followed.

The HFC baseline forms the basis of the phase down of HFC use and was calculated as the average of HFC consumption reported between the years 2020-2022 plus (+) 65% of the HCFC baseline. All are calculated in terms of TCO2eq. This HFC baseline establishes the phase down starting point for Sierra Leone as shown in table below.

Calculation of the HFC baseline

|  | TCO2eq 2020 | TCO2eq 2021 | TCO2eq 2022 | (TCO2eq) total | TCO2eq Average |
| --- | --- | --- | --- | --- | --- |
| HFC | 250,389.95 | 307,210.57 | 386,931.86 | 944,532.38 | 314,844.13 |
| HCFC baseline |  |  |  | 56,076.92 |  |
| 65% of HCFC baseline |  |  |  |  | 36,450.00 |
| HFC baseline |  |  |  |  | 351,294.13 |

Also, the total HFC used for servicing in the various RAC sub-sectors and related direct emissions, were 172.83MT and 386,933.22 TCO2eq respectively.

Distribution of HFC use in RAC sub-sectors (2022)

| Subsector |  | Refrigerants |  |  |  |  |  |  |  | Total | Share of Consumption % |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | R32 | R410A | R134a | R404A | R407C | R407A | R507A | R508B | MT |  |
|  |  | Metric Tonnes (MT) |  |  |  |  |  |  |  |  |  |
| Domestic refrigeration (includes residential use of refrigerators and freezers) |  | 0.00 | 0.00 | 37.55 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 37.55 | 21.73% |
| Domestic Air-Conditioning/ Commercial AC | Split Non-ducted Units | 10.50 | 6.74 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 17.24 | 9.98% |
|  | Split Ducted Units | 0.00 | 4.81 | 0.00 | 0.00 | 3.82 | 8.10 | 0.00 | 0.00 | 16.73 | 9.68% |
|  | Roof Top ducted Units |  | 4.60 |  |  | 4.19 | 6.90 | 0.00 | 0.00 | 15.69 | 9.08% |
|  | Multi Split Units | 0.00 | 0.65 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.65 | 0.38% |
|  | AC Chillers | 0.00 | 2.02 | 2.04 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 4.05 | 2.34% |
| Commercial/ Industrial refrigeration | Centralized Units | 0.00 | 0.00 | 0.48 | 5.99 | 0.00 | 0.00 | 2.99 | 0.00 | 9.45 | 5.47% |
|  | Process Chillers | 0.00 | 0.00 | 2.23 | 7.44 | 0.00 | 0.00 | 3.97 | 0.00 | 13.63 | 7.89% |
|  | Stand-alone | 0.00 | 0.00 | 0.01 | 0.00 | 0.00 | 0.00 | 0.00 | 0.66 | 0.68 | 0.39% |
|  | Condensing Units | 0.00 | 0.32 | 2.73 | 4.43 | 0.00 | 0.00 | 2.73 | 6.84 | 17.06 | 9.87% |
| Marine Refrigeration | Marine Vessels | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00% |
|  | ICE Making Facilities | 0.00 | 0.00 | 0.00 | 1.15 | 0.00 | 0.00 | 1.11 | 0.00 | 2.26 | 1.31% |
| Transport Refrigeration | Refrigerated Trucks | 0.00 | 0.00 | 0.12 | 2.78 | 0.00 | 0.00 | 0.00 | 0.00 | 2.89 | 1.67% |
| Mobile AC | Large MACs | 0.00 | 0.00 | 12.89 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 12.89 | 7.46% |
|  | Small MACs | 0.00 | 0.00 | 22.05 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 22.05 | 12.76% |
| Total use (MT) |  | 10.50 | 19.15 | 80.09 | 21.78 | 8.00 | 15.00 | 10.80 | 7.50 | 172.83 | 100.00% |
|  | % Share | 6.08% | 11.08% | 46.34% | 12.60% | 4.63% | 8.68% | 6.25% | 4.34% | 100.00% |  |

Distribution of HFC use for RAC sub-sectors direct emission in TCO2eq. (2022)

| Subsector |  | Refrigerants |  |  |  |  |  |  |  | Total | Share of Consumption % |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | R32 | R410A | R134a | R404A | R407C | R407A | R507A | R508B | TCO₂eq. |  |
| GWP |  | 675 | 2,088 | 1,430 | 3,922 | 1,774 | 2,107 | 3,985 | 6,808 |  |  |
|  |  | TCO2eq. |  |  |  |  |  |  |  |  |  |
| Domestic refrigeration (includes residential use of refrigerators and freezers) |  | 0.00 | 0.00 | 53,696.50 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 53,696.50 | 13.88% |
| Domestic Air-Conditioning/ Commercial AC | Split Non-ducted Units | 7,089.73 | 14,073.51 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 21,163.24 | 5.47% |
|  | Split Ducted Units | 0.00 | 10,049.02 | 0.00 | 0.00 | 6,774.57 | 17,062.43 | 0.00 | 0.00 | 33,886.03 | 8.76% |
|  | Roof Top ducted Units | 0.00 | 9,612.11 | 0.00 | 0.00 | 7,424.19 | 14,538.30 | 0.00 | 0.00 | 31,574.60 | 8.16% |
|  | Multi Split Units | 0.00 | 1,359.49 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 1,359.49 | 0.35% |
|  | AC Chillers | 0.00 | 4,210.45 | 2,910.05 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 7,120.50 | 1.84% |
| Commercial/ Industrial refrigeration | Centralized Units | 0.00 | 0.00 | 679.25 | 23,473.17 | 0.00 | 0.00 | 11,925.11 | 0.00 | 36,077.53 | 9.32% |
|  | Process Chillers | 0.00 | 0.00 | 3,189.96 | 29163.21 | 0.00 | 0.00 | 15,803.55 | 0.00 | 48,156.72 | 12.45% |
|  | Stand-alone | 0.00 | 0.00 | 19.91 | 0.00 | 0.00 | 0.00 | 0.00 | 4,502.69 | 4522.60 | 1.17% |
|  | Condensing Units | 0.00 | 676.61 | 3,902.23 | 17,391.51 | 0.00 | 0.00 | 10,874.38 | 46,560.78 | 79405.52 | 20.52% |
| Marine Refrigeration | Marine Vessels | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00% |
|  | ICE Making Facilities | 0.00 | 0.00 | 0.00 | 4,510.30 | 0.00 | 0.00 | 4,438.29 | 0.00 | 8,948.59 | 2.31% |
| Transport Refrigeration | Refrigerated Trucks | 0.00 | 0.00 | 167.09 | 10,884.17 | 0.00 | 0.00 | 0.00 | 0.00 | 11,051.26 | 2.86% |
| Mobile AC | Large MACs | 0.00 | 0.00 | 18,439.14 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 18,439.14 | 4.77% |
|  | Small MACs | 0.00 | 0.00 | 31,531.50 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 31,531.50 | 8.15% |
| Total use (MT) |  | 7,089.73 | 39,981.19 | 114,535.63 | 85,422.35 | 14,198.76 | 31,600.73 | 43,041.34 | 51,063.47 | 386,933.22 | 100% |
|  | % Share | 1.83% | 10.33% | 29.60% | 22.08% | 3.67% | 8.17% | 11.12% | 13.20% | 100% |  |

Overarching KIP Strategy

Based on the experience with the HPMP it is evident that the first approach to having a sustainable transitional change in the RAC sector in Sierra Leone begins with the enabling environment that will allow for the smooth transition to low/zero GWP technologies (Stage 1). Sierra Leone aims to follow the established MP reduction targets for HFC use to define the stages of the KIP. Therefore, a total of 4 stages are planned in order to achieve the 80% HFC reduction by 2045.

Sierra Leone fully imports both refrigerants and RAC equipment and will want to use the first stage of the KIP to put in place the necessary legal regime, undertake capacity building for technicians and enforcement agencies, and also undertake stakeholder engagements to get the buy in of all major stakeholders, that will ensure the smooth transition of the RAC industry to low/zero GWP refrigerants. The first stage of the KIP will also be running side by side with the country’s HPMP and hence lessons learned from the ongoing HPMP can also aid in better crafting out other stages of the KIP in the future.

Also the phased approach to HFC reduction allows for new technologies especially those based on low GWP and natural refrigerants to become more accessible worldwide as well as in the country.

In order to develop any detailed strategy for KIP, it is imperative to have a reasonably good understanding of the prevailing conditions in RAC industry today and also understand the trajectory of HFC growth under Business as Usual (BAU) scenarios. These projections assist in identifying the suitable interventions that are required to be undertaken to achieve the necessary impact on the HFC use in the RAC sector.

Historical data on refrigerant usage was captured until 2022 and that was used together with the average GDP growth rate for the country from 2012 to 2022. The average growth rate used for Sierra Leone was 4.09 % according to data from the International Monetary Fund (IMF) (INTERNATIONAL MONETARY FUND, n.d.)

Total HFC emissions projections under BAU Scenario

| HFC emissions (BAU) TCO2eq |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | 2020 | 2021 | 2022 | 2023 | 2024 | 2025 | 2026 | 2027 | 2028 | 2029 |
| HFC consumption | 250,390 | 307,211 | 386,932 | 402,761 | 419,237 | 436,388 | 454,240 | 472,823 | 492,166 | 512,300 |
| Annual increase (%) in HFC consumption |  | 22.69 | 25.95 | 4.09 | 4.09 | 4.09 | 4.09 | 4.09 | 4.09 | 4.09 |
| MLF Compliance target (TCO2eq) |  |  |  |  | 351,294 |  |  |  |  | 316,165 |
| Reduction required (TCO2eq) |  |  |  |  |  |  |  |  |  | 196,135 |

From the estimated emissions in the use of HFC in the RAC sector, under BAU conditions, it is evident that the freeze of 2024 and 10% reduction in 2029 might not be met by Sierra Leone. The KIP strategy aims to address this difference to ensure compliance is achieved while coordinating with ongoing HCFC phase out activities.

The KIP Stage I strategy (2024 -2029) will specifically target the enabling environment to facilitate the freeze on growth of HFC refrigerant in the country and allow for an overall 10% reduction. It will target to do this through legislation and operation of an industry wide quota system.

The following are the planned activities:

- Regulatory frameworks: Putting in the necessary controls to ban and reduce the importation of high GWP gasses and equipment for which there are already low GWP technology alternatives. This target will be on domestic refrigerators, commercial standalone units, single split and multi-split air conditioners. Legislation will also be put in place to also prevent the potential use of HFC’s in other non-RAC sectors such as fire suppression, foam and painting sectors.

Legislation will also be put in place to compel commercial and industrial RAC operators to have adequately sized in-house recovery equipment to minimise their consumption of new HFCs.

Putting in place measures to promote sustainable refrigeration practices and procedures in the RAC sector to reduce leakage and also licensing of selected MAC garages (support 6 garages) to become MAC centre of excellence by EPA/NOU are additional measures to be put in place.

- Demo project: Undertake at least one demonstration project using low GWP technology in the commercial refrigeration sector.

- Capacity building: Developing and implementing targeted training program for RAC technicians, customs and enforcement officers and other professionals. This will include updating the training curricula of the Sierra Leone Technical Institute. The focus of the Technicians training will be for MAC technicians in the leak-proofing, containment and effective recovery of R-134a. The focus for the Customs and other enforcement agencies training will be in line with HFC and other low GWP refrigerants.

KIP stage 1 activities

| Activities proposed (2024-2029) |  | Activity Cost (US$) |  | Tranches (US$) |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | UNEP | UNIDO | Tranche 1 | Tranche 2 | Tranche 3 | Total Cost (US$) |
| 1. Legal & regulatory measures to support HFC phase down |  |  |  |  |  |  |  |
| 1.1 | Coordinate with EC and other relevant key stakeholder’s whiles banning HCFC based equipment to include the ban of RAC equipment using HFC refrigerants with high GWP in the domestic ref., and commercial standalone ref units to HC refrigerants by January 2025. | 0.00 | 10,000.00 | 4,000.00 | 3,000.00 | 3,000.00 | 10,000.00 |
| 1.2 | Support the NOU to establish a national HFC quota system and framework including criteria for quota allocation with provisions for enforcement and monitoring. | 3,000.00 | 0.00 | 3,000.00 | 0.00 | 0.00 | 3,000.00 |
| 1.3 | Legislation to compel commercial and industrial RAC operators to have adequately sized in-house recovery equipment to minimise their purchase of HFCs. | 0.00 | 2,550.00 | 2,550.00 | 0.00 | 0.00 | 2,550.00 |
| 1.4 | Development of a National Cooling Plan: A clear guiding document that will guide the Country to plan, prepare and move along with low GWP and natural refrigerants. In Africa successive administrations tend to take different strategic paths once in office. Thus a comprehensive National Plan that will assist any successive administration understand the current and future Cooling path of the country is very paramount. This plan will cover all the varying cooling sectors and help frame a “Cooling Policy” for all the RAC sub-sectors that will ensure low GWP, and natural refrigerants are adopted and up scaled in the country. The national cooling plan will bring out financial and technical gaps (limitations) of both the HPMP and KIP so that any future cooling activities to be proposed for the country can be used to undertake these gaps. These gaps can be rebate schemes and some expensive demonstration projects that can help to transform the market. | 14,900.00 | 0.00 | 0.00 | 14,900.00 | 0.00 | 14,900.00 |
| 1.5 | Revise ODS regulation to include high GWP HFC refrigerant such as R23 by Jan. 2025. Also allow for the ban of R410A and R404 by 2029. Also, revise Ozone Depleting and other Chemical Regulations to include the ban on HFC chemical in the Fire suppression, foam, aerosols and solvents sectors in the country by January 2026: The survey established that there is no use of HFC in the country excluding the RAC sector. However, it is important to put in the right legislations to prevent any possible import of any HFC based chemicals, for the fire suppression, foam, aerosols and solvents sectors, since they are still globally available. The legislation will clearly spell out that only natural refrigerants or chemicals with no ODS/ GWP can be imported and used. | 7,650.00 | 0.00 | 7,650.00 | 0.00 | 0.00 | 7,650.00 |
| 1.6 | Revise Building codes, MEPS and labels for RAC units: a. Building codes will be revised to mention the use of low GWP refrigerants and other technologies that promote the use of relatively less refrigerants such as water chilled systems for buildings. Low GWP refrigerants that will be promoted will be hydrocarbons, HFO’s and to the extreme R32. This will be by 2025. b. MEPS will also be revised to mention the kind of Refrigerant that can be used apart from the energy efficiency level. The GWP of Affordable low GWP refrigerants will be proposed as a benchmark to make it affordable for end-users. This will be by 2025. | 14,900.00 | 0.00 | 14,900.00 | 0.00 | 0.00 | 14,900.00 |
|  | Sub total | 40,450.00 | 12,550.00 | 32,100.00 | 17,900.00 | 3,000.00 | 53,000.00 |
| 2. Enforcement of HFC controls |  |  |  |  |  |  |  |
| 2.1 | Revise and upgrade customs training curriculum to include HFCs, HCs, natural refrigerants, new HS code etc. | 10,100.00 | 0.00 | 10,100.00 | 0.00 | 0.00 | 10,100.00 |
| 2.2 | TOT for customs officers on New revised curriculum (10 custom officers). | 1,000.00 | 0.00 | 0.00 | 500.00 | 500.00 | 1,000.00 |
| 2.3 | Organizing workshops and training for clearing agents on the new revised curriculum. | 5,000.00 | 0.00 | 2,500.00 | 2,500.00 | 0.00 | 5,000.00 |
|  | Sub total | 16,100.00 | 0.00 | 12,600.00 | 3,000.00 | 500.00 | 16,100.00 |
| 3. Capacity building |  |  |  |  |  |  |  |
| 3.1 | Upgrade training curricula for RAC vocational/technical instructions to include HFCs HCs and natural refrigerants. | 10,600.00 | 0.00 | 10,600.00 | 0.00 | 0.00 | 10,600.00 |
| 3.2 | Develop a CO2 training programme at the centre of excellence training centre. | 10,600.00 | 0.00 | 10,600.00 | 0.00 | 0.00 | 10,600.00 |
| 3.3 | Awareness creation on HFCs, HCs, natural refrigerants and Kigali Implementation plan (KIP) among RAC importers, distributors and retailers of refrigerant and equipment’s. | 2,800.00 | 0.00 | 1,400.00 | 1,400.00 | 0.00 | 2,800.00 |
| 3.4 | Awareness creation for Built Environment professionals and procurement officers on HFCs, HCs, natural refrigerants, design, specify and procure of RAC Units for end-users. | 2,800.00 | 0.00 | 1,400.00 | 0.00 | 1,400.00 | 2,800.00 |
| 3.5 | Stakeholder’s engagement with Vehicle importers to frame a National Policy for the Mobile AC sector to shift from use of R134a to HFO’s or any globally acceptable natural refrigerant for vehicle air conditioning. | 1,300.00 | 0.00 | 1,300.00 | 0.00 | 0.00 | 1,300.00 |
| 3.6 | License of selected MAC garages (support 6 garages) to become MAC centre of excellence by EPA/NOU. | 0.00 | 6,200.00 | 6,200.00 | 0.00 | 0.00 | 6,200.00 |
|  | Subtotal | 28,100.00 | 6,200.00 | 31,500.00 | 1,400.00 | 1,400.00 | 34,300.00 |
| 4. Demonstration of pilot projects on commercial refrigeration sector |  |  |  |  |  |  |  |
| 4.1 | Demonstration project for R290 monoblocks for +ve/-ve temps. Size (1/3- 2.5HP) installation, commissioning and training at the centre of excellence. | 0.00 | 46,000.00 | 0.00 | 46,000.00 | 0.00 | 46,000.00 |
|  | Subtotal | 0.00 | 46000.00 | 0.00 | 46000.00 | 0.00 | 46000.00 |
| 5. Other gender mainstreaming |  |  |  |  |  |  |  |
| 5.1 | Awareness creation on the RAC industry for junior level students (50% male, 50% females). | 6,600.00 | 0.00 | 3,300.00 | 0.00 | 3,300.00 | 6,600.00 |
| 5.2 | Encouraging women role models presentation in all KIP Implementation workshop. | 6,000.00 | 0.00 | 2,000.00 | 2,000.00 | 2,000.00 | 6,000.00 |
|  | Subtotal | 12,600.00 | 0.00 | 5,300.00 | 2,000.00 | 5,300.00 | 12,600.00 |
| 6. Monitoring |  |  |  |  |  |  |  |
| 6.1 | Project Monitoring Unit (PMU) support and coordination. | 12,600.00 | 5,400.00 | 7,000.00 | 6,000.00 | 5,000.00 | 18,000.00 |
|  | Subtotal | 12,600.00 | 5,400.00 | 7,000.00 | 6,000.00 | 5,000.00 | 18,000.00 |
|  | TOTAL | 109,850.00 | 70,150.00 | 88,500.00 | 76,300.00 | 15,200.00 | 180,000.00 |

| # I. BACKGROUND |  |
| --- | --- |

## I.1	Policy/legislative/regulatory and institutional frameworks related to HFC

### Policy/legislative/regulatory framework

Ratification Status:

Sierra Leone adopted the Kigali Amendment, the most current modification, on 20th June, 2020, as part of its commitment to the Montreal Protocol. Sierra Leone is categorized as Group 1 of the Article 5 nations and is required to comply with the Kigali Amendment's HFC freeze in 2024 and the first HFC reduction step, which is to achieve a 10% reduction in baseline HFC consumption by the first of January 2029. The HCFC Phase out Management Plan (HPMP), which is presently in progress, is supporting Sierra Leone commitment to phase out HCFCs by 2030 with a 0.56% servicing tail.

Montreal Protocol relevant regulatory controls:

Sierra Leone, being party to the Montreal Protocol, committed and aligned itself with other nations in phasing out the consumption of the controlled ODS under the Montreal Protocol phase out targets.

In this regard the National Ozone Unit (NOU) was established under the Environment Protection –Sierra Leone (EPA-SL) to coordinate the activities on the phasing out consumption of the ODS in the country.  In 2008, the Government of Sierra Leone passed an Act in Parliament for the establishment of the Environment Protection Agency and for the protection of the environment and this 2008 EPA Act has been repeal and replaced with the EPA Act 2022. Part VII of that 2022 Act addresses ozone issues targeting banned and controlled ozone depleting substances. To accelerate the implementation of the Montreal Protocol and the Environment Protection Agency Act of 2008 as amended in 2010 and the new 2022 Act, the NOU developed an Ozone Depleting Substances regulation of 2010 and came into force in 2011.

The regulation of 2010 targets specifically the prohibition of the importation of refrigerators, air conditioning containing controlled substances, importation of second handed equipment containing banned or controlled substances as stipulated in the Part V of the EPA Act, 2008 and Part VII of the EPA Act, 2022, registration and certification of servicing workshops, establishment of certification scheme for technicians, establishment of an import /export licensing system etc.

There is a functional quota and license system in place for HCFC. The current regulation is also used to license the importation of HFCs but not exhaustive to include the quota system. The HFC license system only assists in data collection, tracking and verification.  However, the draft regulation which is yet to be passed into law will bring into force additional regulatory actions that will limit consumption of HFCs.

The private sector is also regulated through the acquisition of an environmental permit from EPA-SL wherein they are expected to report on a quarterly basis ozone protection. The NOU is also obliged to undertake any assessment of the phase-out programme and encourage stakeholders to switch to ODS alternatives.

The Finance Act of 2014 requires importers and exporters to declare as required by law all products for onward inspection at all border crossing points. Similarly, the Sierra Leone Customs Acts 2011 discourage the issue of smuggling of goods in and out of the country through the institution of strictly penalty.

Other regulatory provisions related RAC equipment:

The mandate for Sierra Leone’s NAP is grounded in its National Climate Change Strategy and

Action Plan (NCCSAP) and its latest Medium-Term National Development Plan (MTNDP 2019-2023), which includes a cluster on addressing vulnerabilities and building resilience. The NAP builds on these existing policies and supports their implementation. Additionally, the NAP is aligned with the National Climate Change Policy Framework (NCCPF, 2012), the updated Nationally Determined Contribution (NDC, 2021), National Communications to the UNFCCC and National Adaptation Programme of Action (NAPA). The NAP process supports the implementation of these policies and the forthcoming updated NDC.

### Institutional framework

The key stakeholders in the HFC survey are the importers, wholesalers and distributors, manufacturing companies, users such as RAC technicians and owners of appliances. These provide information on quantities imported or used. Enforcement authorities such as: NRA Customs Officers, Environmental Officers, the Police, Law Officers and local authority inspectors work closely with the Government to enforce provisions of the regulations, and these provided information on enforcement mechanisms. All these organization are represented in the National Ozone Steering Committee which advises Government in formulating and implementing policies as well as creating and enforcing regulations to prohibit, control and monitor the imports, use, disposal and export of HFC.

Shown in Table 1 are the key stakeholders and their roles.

| Key Stakeholder | Role |
| --- | --- |
| National Ozone Unit | Hiring of a consultant, organizing Inception Workshops, designing and conducting training of the questionnaires, administrators, desk study, monitoring and supervising data collection, editing, approving and submission of Final Report. |
| National Revenue Authority Customs department | Providing data on imports |
| Statistics Sierra Leone | Statistical Data on imports |
| Refrigeration Engineers and Technicians Association | Assist in the data collection |
| Importers | Data on imports |
| Manufacturing companies | Data on ODS alternatives used in manufacturing |
| ODS Alternative users | Providing data on uses of ODS Alternatives |
| National Consultant | Facilitate data collection, collecting and producing a draft report |

Table 1: The key stakeholders and their roles

The National Ozone Unit (NOU) is a unit within the Division of Chemicals Control and Management in the Directorate of Environmental Health and Safety in the Environment Protection Agency under the Ministry of Environment and Climate Change, reporting to the Executive Chairman who is the head of the Agency.  This is schematically illustrated in Figure 1.

The NOU is headed by the Ozone Project Manager.   A Project Assistant helps the Project Manager with administrative duties.  The Officers are paid from the Institutional Strengthening Project which is funded by the Multilateral Fund through the United Nations Environment Programme Compliance Assistance Programme. The Government provides office space and furniture as well as other logistical support. The Project Manager is responsible for interacting with internal and external stakeholders on matters relating to ODS phase out/HFC phase down, such as drafting of project proposals, data reporting, training of refrigeration technicians and customs officers, enforcement of regulations, enunciation of policy, publicity and awareness raising.

Executive Chairperson Environmental Protection Agency – Sierra Leone

Deputy Director Environmental Health and Safety

Head of Chemical Controls and Management

National Ozone Officer - NOU

Assistant Ozone Officer - NOU

Administrative Secretary - NOU

Executive Chairperson Environmental Protection Agency – Sierra Leone

Deputy Director Environmental Health and Safety

Head of Chemical Controls and Management

National Ozone Officer - NOU

Assistant Ozone Officer - NOU

Administrative Secretary - NOU

Figure 1: Schematic representation of the Institutional arrangements

### RAC training framework

The training infrastructure is a crucial element of the institutional framework and essential to the successful execution of all tasks associated to the RAC sector.

Training Institutes

As of Year 2022, the total number of RAC graduate technicians in the country were 204. Out of the 204 technicians, 183 were males and 21 females. Also, the survey established that there were about 2,408 RAC technician across the country (see Table 2).

Certification of RAC Technicians

In Sierra Leone, one can practice as a RAC technician after obtaining any of the following level of certification in RAC studies;

i.	National Technical Certificate I (2years)

ii.	National Diploma (3 years)

iii.	Higher National Diploma (Refrigeration and Air conditioning option) (5 years)

Table 2: Overview of RAC training institutes

|  | Name of School | Location | Description | Personnel |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | (Province or Region) | (Authority, Type of Certificates) | Senior Instructors |  | Trainers |  | Average Number of graduates annually |  |
|  |  |  |  | Male | Female | Male | Female | Male | Female |
| TVET (Technical Schools, Basic Education) | Government Technical Institute | Kambia | National Technical Certificate(NTC) | 1 | 0 | 1 | 0 | 8 | 0 |
|  | Government Technical Institute | Kono | National Diploma (ND) | 1 | 0 | 1 | 0 | 18 | 1 |
|  | Government Technical Institute | Moyamba | National Technical Certificate(NTC) | 1 | 0 | 1 | 0 | 10 | 0 |
|  | OIC Bo | Bo | National Technical Certificate(NTC) | 2 | 0 | 1 | 0 | 10 | 0 |
|  | OIC Makeni | Makeni | National Technical Certificate(NTC) | 2 | 0 | 2 | 0 | 15 | 0 |
| Technical Universities | Eastern Technological University | Kenema | Higher National Diploma (HND) | 2 | 0 | 3 | 0 | 18 | 1 |
|  | Milton Margai Technological University | Freetown | Higher National Diploma (HND) | 2 | 0 | 1 | 0 | 19 | 0 |
|  | Freetown Polytechnic | Kissy Campus Freetown | Higher National Diploma (HND) | 2 | 0 | 4 | 0 | 63 | 7 |
|  | Arm Forces Technical College | Wilberforce Freetown | Higher National Diploma (HND) | 1 | 0 | 2 | 0 | 22 | 12 |

## I.2	Overview of the HCFC phase-out management plan implementation

Sierra Leone’s consumption of Hydrochlorofluorocarbons (HCFCs) is in the servicing of refrigeration and air conditioning (RAC) equipment.

The HPMP Stage-I for Sierra Leone was approved at the 65th Meeting of the Executive Committee with a total funding of US$210,000 plus implementing agencies support cost for the period 2011 to 2020 to reduce consumption of HCFCs by 35% of the baseline. The established baseline consumption of HCFCs for Sierra Leone was 30 metric tons.

The Government of Sierra Leone (GoSL) had made tremendous progress on the implementation of activities under stage I of the Hydrochlorofluorocarbon Phase-out Management Plan (HPMP). The HPMP Stage-I has successfully enabled Sierra Leone to freeze HCFC baseline in 2013, and achieve 10 percent reduction in consumption of HCFC by 2015 in line with the accelerated HCFC phase-out schedule under the Protocol.

Sierra Leone had already achieved more than 35% HCFCs consumption reduction before 2020 agreed target under the Montreal Protocol. The HPMP Stage-I has successfully phased out a total of 0.58 ODP tons of HCFCs in the country as of 2020.

Furthermore, the successful implementation of HPMP Stage-I has achieved a net direct emission reduction of 18,907 tons of carbon dioxide equivalent per year. The stage II implementing activities of the HPMP commence in January 2023.

HPMP Stage I has only recently been completed. Below is a summary of the activities successfully completed:

- Strengthen the capacity of Customs Officers and other law enforcement officers.

- Strengthen the capacity of Refrigeration Technicians, and training institutes.

- Strengthening of Regional Centres of Excellence and Incentive Programme for Commercial and Industrial Refrigeration End-users and Development of a comprehensive program for reduction of HCFC and Carbon emissions in the Refrigeration and Air Conditioning Sector.

- Monitoring and evaluation of the implementation of HPMP

The HPMP Stage II for Sierra Leone is currently ongoing. The following are the main activities included into the Stage II and an update on completed activities:

- Facilitate the development and implementation of National technical standards in the RAC sector for safe use of energy efficiency low GWP RAC systems and promotion of green procurement of Refrigeration and Air-conditioning (RAC) systems.

- Strengthen the enforcement of ODS regulations including capacity enhancement of customs officers, Consumer Protection Officers and other Law Enforcement Officers.

- Establishment/Strengthen of a certification scheme, training and certification of 300 refrigeration technicians, strengthening the refrigeration association and upgrading of national refrigeration codes of practice.

- Strengthening the centres of excellence through provision of toolkits, establishment of refrigerant recovery and re-use scheme, including set up of one reclaim centre, technical assistance and end user awareness raising and capacity building on hydrocarbon alternative refrigeration technologies.

- Project coordination, monitoring, evaluation and reporting.

Whilst the country has started implementing the activities under Stage II, the presence of a KIP strategy will provide a good opportunity to allow Sierra Leone to adjust, compliment and synergise ongoing and planned activities of the HPMP with those planned under the KIP with the overall objective of ensuring that HFC reduction is an integral part of planning and execution of all initiatives.

Some of the lessons discovered throughout the HPMP have been taken into consideration and, to the extent possible, will be addressed effectively under the KIP:

- Policy Update and Enforcement:

The Prohibition of Ozone Depleting Substances Regulation 2010.

Change in Political Administration, Limited knowledge on Part of Judiciary and Parliament on some of the key terminologies and chemicals of interest in the Montreal protocol.

- Customs and Trade Authorities Training:

The Country successfully built the capacity of   487 Customs and other law enforcement Officers who have been trained in combating illegal trade, Identification of refrigerants, facilitating legal trade etc.

The frequent changes of Customs and other law enforcement officers always creates the pressure or gaps in knowledge.

- Training of Refrigeration Good Practice:

About 379 RAC technicians has benefited from Trainings under the stage I and their capacities were built in the provision of the Montreal Protocol, Good Refrigeration Practices, Flammable Refrigerants handling, Environmental Impacts associated with bad refrigeration practices, retrofitting etc.

The availability of centres of excellence in most part of the country for technicians to access critical tools remains a major challenge.

- Certification of Servicing Technicians:

A total of 197 technicians were trained and Licensed under this tranche

The initial challenge has to do with the centralized nature of the training for certification and licenses which was only in the Capital city, but the NOU in recent years has decentralized it trainings to the regions which has created attraction and participation

- Establishing RRR Scheme:

Few RRR equipment’s were procured and deployed in two of the training centres.

- Updating National Standards:

The only standard developed was the certification standard for RAC practitioners: Gold, Silver and Bronze. This has to do with their level of education experience in the RAC sector.

- Technical and Technological Awareness:

Several Technical and Technological Awareness activities were undertaken e.g. TV & Radio Programs, Community Engagements and Stakeholder Sensitization events

Accessibility during the raining season remains an historic challenge as some of the areas of interest have poor road networks.

- Support to National Associations:

The NOU via the support of the MP provided basic tools and also provided technical support through trainings to National Associations like the RAC, Importers, and other Enforcement Bodies - Traders Union. In addition, equipment like recovery Machine, Recovery cylinder, RRR Machine, Refrigerants Identifiers were provided to RAC Technicians Association in Kono, Bo, Freetown and Makeni.

- Incentive schemes and demo/pilot projects:

There was an Incentive Scheme which was extended to the people in the Fisheries sector and Supermarket. However, there was no Demo Project.

The funds for the implementation of the incentive scheme was limited.

- Green Public Procurement:

The country benefited by participating in a workshop organized by UNEP in Dakar, Senegal during which the NOU and a representative from the National Public Procurement Authority attended.

Limited knowledge of our public procurement Institutions and practitioners is affecting Green Procurement especially RAC Green Procurement.

- Gender mainstreaming activities:

The NOU has discussed via its public sensation activities topic of Gender mainstreaming within the RAC sector and has placed more emphasis over the years on female practicing in the RAC Industry. It also provided scholarships for females who opt to undertake training in RAC training.

The topic itself is new and cultural acceptability serves a strong opposition. Government support in motivating the weaker gender has been low.

## I.3 Implementation status of HFC-related activities

Sierra Leone has only received funding for RAC activities from the MLF and has no ongoing or planned projects outside the MLF funded project.

# II. HFC CONSUMPTION BY SUBSTANCE AND SECTOR

## II.1	Methodology and validation

### Preparatory work

An effective and timely data gathering effort depends on careful planning beforehand. The National Consultant team was made up of specialists with a wealth of RAC sector knowledge, familiarity with the specifications of Multilateral Fund (MLF) projects, and participation in comparable data gathering activities for the RAC sector in the past.

Based on the kind of equipment, the RAC industry in the nation has been divided into many sectors (Table 1) for the purpose of gathering data and thoroughly studying RAC applications. This classification helps to comprehend the HFC consumption trends and equipment base (stock) in order to create interventions that are suitable for addressing the existing trends and bringing them into line with the Kigali phase-down timeframe.

- Methodology for data collection

Due to the national election campaign, as at the time of the data collection, several procedures for data collection were utilized during the two-month countrywide poll.

The material used to create the content of this desk review was gathered through an organized evaluation of the survey-relevant papers that were accessible, as well as through online research. The NOU and the national consultant did a desk assessment to identify significant stakeholders and laws pertinent to the survey. The desk review assisted the unit in developing its data gathering approach. Stakeholders from the five regions of the nation were invited to an initial workshop, where they were informed about the project and the approach to be used in gathering the necessary data. The NOU and the national consultant determined the sample size based on the population and geography of the country and adopted the questionnaire developed by the Compliance Assistance Programme of UNEP Ozone Action.

The population of this survey includes the main districts headquarter towns across the country. These include, residential homes, big business using refrigeration and air condition, government buildings, vehicles etc.

The questionnaires were distributed to identified key stakeholders that were dealing with ozone issues within the country.

The questionnaires developed were used to collect data from the following sectors: refrigeration and air conditioning servicing; health; commercial and industrial sectors. The import data were sourced from the National Revenue Authority (Customs department), marine and the National Ozone Unit.

During the inception workshop, stakeholders who were identified as the potential respondents in the desk review were invited to make their inputs on how they are expecting the survey to be administered. The questionnaire was pilot tested, and all unclear sections were revised.

The enumerators were selected from the list of trained and certified RAC technicians and were trained on data collection techniques. Each enumerator was given a covering letter that accompanied the questionnaires explaining why the respondents should provide the requested information as a means of giving confidence and credibility to the entire process. The respondents were guaranteed that the information collected would be handled confidentially.

The data collected were sent to the lead consultant for compilation, analysis and production of the National Survey Report using the template and data tables developed by the MLF and reviewed by CAP Regional Office for Africa.

Where the NOU detected some inconsistencies or where the data collected were not clear or insufficient, the technicians were asked to revisit the facilities to get the required data.

At the end of data collection, the NOU together with some technicians and the lead consultant undertook a five days data verification and upgrading exercise to enhance the total coverage with reference to the sample size that was selected.

- Questionnaire

The KIP survey questionnaires are shown in Appendix C.

As per the KIP survey and reporting guidelines, the RAC equipment are defined as follows as shown in Table 3.

Table 3: RAC equipment sub sectors

| Sub-sector |  | Equipment type |
| --- | --- | --- |
| Refrigeration (REF.) | Domestic ref. | Fridge, Freezer & combined Fridge/Freezer, double doors |
|  | Commercial & Industrial ref. | Stand-alone unit (display cabinet, dispenser unit) |
|  |  | Condensing unit (cold stores, supermarkets, industry) |
|  |  | Centralised system (cold storages, supermarkets) |
|  |  | Process chiller |
|  | Transport ref. | Refrigerator trucks/trailers |
|  | Marine ref. | Ashore-based ice plants & fishing vessels and ice making facilities |
|  |  | On-board cooling systems |
| Air Conditioning (AC) | Unitary AC (Stationary) | Self-contained (window) unit |
|  |  | Single Split unit (non-ducted, ducted) |
|  |  | Multi split (VRV/VRF) |
|  |  | Rooftop packaged (ducted) |
|  | Chiller | Comfort AC Chiller |
|  | Mobile AC (MAC) | Small vehicle AC (Saloon car, light commercial) |
|  |  | Large vehicle AC (bus) |

- Interviews:  Interviews were also other approach that was used to gather information from stakeholders.

Sample Size Calculation

The sample size formula is as follows:

Where

n=z2*p*q+(e2)(e2)+[(z2*p*q)/N]

n 	is the sample size.

z 	is the selected critical value of the desired confidence level, which is associated with the level of confidence required for the estimate (often set at 1.96 for a 95% confidence level)

p 	is the estimated proportion of an attribute present in the population

q 	Represents the complement of p (i.e., q =1−p)

e 	is the margin of error, which indicates the maximum allowed difference between the sample estimate and the true population proportion

N 	is the size of the finite population

Data Collection Challenges

The following are the challenges faced during the data collection:

- The electioneering process repeatedly obstructed the schedule and movement for data collection across the country.

- The heavy down pour of rains during which the survey was conducted was a great challenge.

- The business people and some public institutions find it very difficult to release information concerning their business despite enumerators were given a letter of introduction.

- Fragmented secondary data sources also limited the timely completion of the data gathering.

- Time and funds allocated for data gathering was limited.

Data Collection Team

The data collection team were made up of the following persons as indicated in Table 4.

Table 4: Tasks, Compositions, Roles, and Responsibilities of Personnel’s

| Tasks | Compositions | Roles and Responsibilities |
| --- | --- | --- |
| Enumerators | RAC Technicians | To collect primary data from the field |
| Data Collection Supervisors | Regional Manager of the EPA-SL Regional Offices and Two Senior Staff at the EPA-SL Head Office | To compile completed data gathering tools for onward transmission to the lead consultant. To ensure enumerators gain access wherever they had some kind of restrictions. Also to provide the needed explanation as to why the data collection is important for national development. |
| Data Collection coordinator | Project Consultant | Coordinating and overseeing all data collection across the country. |
| Data Analysis | Project Consultant and Project deputy consultant | Master sheets data inputs, data sorted by RAC equipment sector. |
| KIP Questionnaires and Survey guidelines, Expect technician | International UNEP KIP Consultant | KIP Questionnaires, Survey guidelines, overseeing data collection, review of survey |
| National Supervisors | Senior Ozone Officer and the Principal Secretary | Assisting and supervising data, reviews |
| Field Surveyor | Project Consultant and Project assistance consultant | Data collection |

Data Collection Source Identified

Information was gathered by distributing questionnaires to importers, distributors, end users, and relevant authorities such as the National Ozone Unit (NOU) and the Energy Commission. This data was then compiled and analysed to formulate an in-depth comprehension of the existing HFC (Hydrofluorocarbon) equipment in the country. The focus is on understanding the HFC-related necessities essential for addressing the maintenance and servicing demands of this equipment inventory shown in Table 5.

Table 5: Source of Data for RAC sector

| Description | Source of Data |
| --- | --- |
| Self-contained | Large Hotels, commercial buildings with offices, hospitals, importers |
| Single split, non-ducted | Importers/wholesalers, Residential, Commercial Buildings, hotels, industrial, restaurants, schools, Import Data |
| Single split ducted | Commercial buildings, RAC Contractors |
| Roof top ducted | Large Hotels |
| Multi-Split | Large Hotels, Commercial buildings, hospitals |
| AC Chiller | Industrial cold storage, large hotels |
| Domestic Refrigeration | Residential, Importers, hotels, restaurants, supermarkets, Import Data |
| Commercial/ Industrial Refrigeration | ###### Large Supermarkets, Cold Storages, Industrial level cold storages (fisheries sector), Sierra Leone Fishing Authority (SLFA) |
| Mobile air conditioners | Vehicle Importers, Sierra Leone Licensing Authority (SLLA), Vehicles workshops, RAC contractors |
| Transport Refrigeration | User Companies Wholesalers, SLLA |
| Marine Refrigeration | Data of Fishing vessels was catered from SLLA and SLFA. |
| Fire Suppression System | SFRSA, firefighting contractors, hotels, telecommunication companies |

## Data Validation

The following approach were used to validate the data collected:

- A dedicated data validation exercise was conducted by a team comprising of a representative of the NOU, Lead Consultant, RAC Technicians that were not part of the data collectors and a civil society representative.

- Cross reference with exist database sources was done for secondary data sources especially for the socioeconomic data and import data.

- A national validation works was conducted.

## II.2	HFC consumption data (2016- 2022)

Sierra Leone is dependent on refrigerant imports to meet the servicing needs of the refrigeration and air conditioning sector (RAC).

While the country has been reporting HCFC imports under the Article 7 data reporting requirement of the Montreal Protocol, HFCs have recently been incorporated into the overall data reporting regime and thus the has been reporting HFC imports since 2017 as shown in Table 6.

The Table provides a general overview of HFCs and HCFC refrigerants consumed in the country over the last seven (7) years.  The consumption trends also highlight the changing landscape of refrigerants overtime. HCFC use has seen a steady decline in line with the HCFC phase out deadline. The HFCs that are currently the most common alternative to HCFCs are thus witnessing a progressive increase in quantities.

Table 6: Refrigerant (HFC & HCFC) consumption (2016- 2022) in metric tons (MT)

| Refrigerants | GWP | Consumption (Metric Tonne) |  |  |  |  |  |  | % of Refrigerant share in 2022 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 | 2022 |  |
| R32 | 675 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 10.50 | 6.08% |
| R134a | 1,430 | 0.00 | 0.00 | 38.30 | 40.30 | 65.96 | 70.58 | 80.09 | 46.34% |
| R404A | 3,920 | 0.00 | 10.30 | 12.3 | 12.00 | 14.65 | 17.85 | 21.78 | 12.60% |
| R407A | 2,107 | 0.00 | 4.90 | 5.00 | 6.30 | 6.50 | 10.50 | 15.00 | 8.68% |
| R407C | 1,774 | 6.10 | 3.20 | 4.40 | 5.70 | 5.10 | 7.16 | 8.00 | 4.63% |
| R410A | 2,088 | 0.00 | 7.40 | 7.90 | 8.90 | 14.50 | 18.34 | 19.15 | 11.08% |
| R507A | 3,985 | 0.00 | 0.00 | 0.00 | 0.00 | 6.23 | 7.23 | 10.80 | 6.25% |
| R508B | 3,985 | 0.00 | 0.00 | 0.00 | 0.02 | 3.05 | 5.20 | 7.50 | 4.34% |
| Total |  | 6.10 | 25.80 | 67.90 | 73.22 | 115.99 | 136.86 | 172.83 | 100% |

In 2022, R134a was the dominant refrigerant consumed making up 46.34% of total HFC consumption. The other HFCs namely R508B, R407C, R32, R507A, R407A, R410A and R404A accounted for 4-13% of total HFCs. Due to significantly different GWP between refrigerants, variations in absolute quantities of specific refrigerants do not reflect a similar pattern in CO2eq emissions. For instance, R134a constitutes 46.34% of the total refrigerant used, but emits 29.60% of total CO2eq emissions.  In contrast R404A which amounts for only 12.60% of total HFC refrigerant quantities is responsible for 22.08% of the CO2eq emissions (see Table 7).

This is an important factor that defines the kind of strategy Sierra Leone must adopt in order to ensure that the overall CO2eq emissions are contained in order to comply with the Kigali phase down targets.

Table 7: CO2eq emissions for HFC refrigerants reported in 2022

|  | Refrigerants |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | R32 | R410A | R134a | R404A | R407C | R407A | R507A | R508B |
| % of total refrigerants | 6.08% | 11.08% | 46.34% | 12.60% | 4.63% | 8.68% | 6.25% | 4.34% |
| TCO2eq (2022) | 7,089.73 | 39,981.19 | 114,535.63 | 85,422.35 | 14,198.76 | 31,600.73 | 43,041.34 | 51,063.47 |
| % of total emissions | 1.83% | 10.33% | 29.60% | 22.08% | 3.67% | 8.17% | 11.12% | 13.20% |

### A.	List of Importers

Sierra Leone will enforce a quota system for HFCs from 2024 onwards, when the HFC controls come into force. Currently, HFC imports have been allowed based on requests received by the EPA from importers and the relevant import permits were issued for these imports. There are seven (7) registered importers of refrigerants in the country detailed in Table 8.

Table 8: List of Importers of HFCs and HCFC

|  | Company name | Imported quantity 2022 (kg) | Imported quantity 2021 (kg) | Imported quantity 2020 (kg) |
| --- | --- | --- | --- | --- |
|  | Sierra Fishing Company | R-22-3,567 R134a-1,786 R410A-689 | R-22- 4,300 R134a- 1,450 R410A- 764 | R22 - 2,400 R134a - 1,234 |
|  | Ok Fishing Companying | R-22- 3,000 R134a- 1,765 R410A- 698 | R-22- 3,500 R134a- 2,450 R410A- 654 | Operation was Suspended due to COVID-19 |
|  | International Cooling Investment | R-22- 3,000 R134a- 3,590 R410A- 1,345 R32 – 400 R407A- 160 R404A - 90 | R-22- 3,870 R134a- 3,000 R410A- 1,045 R32 – 300 R407A- 100 R404A - 100 | R-22- 2,000 R134a- 3,590 R410A- 1,345 R407A- 100 |
|  | Kombra Fishing Company | R-22-1,000 R134a-1,786 | R-22-1,200 R134a-1,644 | R-22- 1,500 |
|  | Agaa Cooling | R-22- 2,000 R134a - 6,765 R32 – 300 R407A- 460 | R-22- 2,0145 R134a- 5,340 R410A- 1,045 R407A- 789 | R-22- 2,500 R134a- 3,590 R410A- 1,345 R407A- 100 |
|  | Chambers Investment | R-22- 2,450 R134a- 6,070 R410A- 3,645 R407A- 100 R32 - 200 | R-22- 2,500 R134a- 5,550 R410A- 2,345 R407A- 100 | R-22- 3,000 R134a- 3,000 R410A- 1,500 R407A- 200 |
|  | Sabco Fishing Company | R22- 1,200 R134a- 2,789 | R22-1,500 R134a - 2,462 | R22-1,800 R134a - 678 |
|  | A.J Barrie Ent | R22 - 2,500 R134a - 7,421 R410A - 2,700 | R22 – 2,456 R134a - 6,754 R410A – 3,456 | Was not in Operation by then |

### B.	HFC baseline

Under the Kigali Amendment, Sierra Leone has been listed as an Article 5, Group 1, country with respect to the HFC phase down schedule to be followed.  The HFC baseline forms the basis of the phase down of HFC use is to be calculated as the average of HFC reported between the years 2020-2022 +65% of the HCFC baseline. All are calculated in terms of CO2eq. This HFC baseline establishes the phase down starting point for Sierra Leone as shown in Table 9.

Table 9: Calculation of the HFC baseline

|  | TCO2eq 2020 | TCO2eq 2021 | TCO2eq 2022 | (TCO2eq) total | TCO2eq Average |
| --- | --- | --- | --- | --- | --- |
| HFC | 250,389.95 | 307,210.57 | 386,931.86 | 944,532.38 | 314,844.13 |
| HCFC baseline |  |  |  | 56,076.92 |  |
| 65% of HCFC baseline |  |  |  |  | 36,450.00 |
| HFC baseline |  |  |  |  | 351,294.13 |

### Prices of refrigerants

In order to understand the market dynamics of the refrigerants, the survey considered the prices of all the refrigerants consumed in Sierra Leone for the period 2016 to 2022. Figure 2 shows the average prices of refrigerants from 2016 to 2022. It is worth noting that most importers of HFC refrigerants are for their own consumption, or for RAC servicing contractors.

Figure 2: Prices of Refrigerant

Figure 2 illustrates a noteworthy trend: in 2019, R32 refrigerant was introduced to the market. Meanwhile, the prices of alternative refrigerants, including R134a, R404A, R407A, R407C, R410A, R507A, R290, and R600a, have been steadily on the rise since 2016.

Also, R22 had an appreciable increase in price from 2016 upward as well.

### RAC service technicians

As of Year 2022, the total number of RAC graduate technicians in the country were 204. Out of the 204 technicians, 183 were males and 21 females. Also, the survey established that there were about 2,408 RAC technician across the country (see Table 10).

Table 10: Number of technicians working in the RAC sector

| Type of equipment served | Number of RAC technicians |  | Total Number of technicians |
| --- | --- | --- | --- |
|  | Formal/registered | Informal/unregistered |  |
| Unitary Air conditioners/ Domestic Refrigeration | 277 | 1,170 | 1,447 |
| Mobile Air conditioners | 60 | 576 | 636 |
| Transport refrigeration | 10 | 227 | 237 |
| Commercial and Industrial Refrigeration | 30 | 58 | 88 |
| Total | 377 | 2,031 | 2,408 |

## II.3	Sectoral distribution of HFCs

Sierra Leone has no assembly or manufacturing facility of RAC equipment. All refrigerant used in the country is to meet the servicing needs of installed equipment in the country (see Tables 11, 12 and 13).

Table 11:  Overall stocks of RAC equipment (2022)

| Sub Sector |  | Estimate Stock RAC Equipment | Recorded Surveyed Equipment |
| --- | --- | --- | --- |
| Domestic Ref. | Refrigerator/Fridge | 2,668,753 | 2,001,565 |
| Commercial Ref. | Condensing Unit | 163 | 122 |
|  | Standalone Unit | 10,367 | 9,283 |
| Industrial Ref. | Process Chillers | 30 | 24 |
|  | Centralized Unit | 10 | 5 |
| Transport Ref | Truck Ref | 65 | 49 |
| Marine Ref. | Marine Vessels | 30 | 16 |
|  | ICE Making facility | 10 | 6 |
| Domestic AC | Split Non-ducted Unit | 665,451 | 499,088 |
| Commercial AC | Split-ducted Unit | 10,897 | 9,300 |
|  | Multi-split Unit | 305 | 257 |
|  | Roof Top-ducted Unit | 410 | 306 |
|  | AC Chillers | 100 | 74 |
| Mobile AC | Small MAC | 81,699 | 61,274 |
|  | Large MAC | 14,417 | 10,813 |
| Total |  | 3,432,268 | 2,592,182 |

| Subsector |  | Refrigerants |  |  |  |  |  |  |  | Total | Share of Consumption % |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | R32 | R410A | R134a | R404A | R407C | R407A | R507A | R508B | MT |  |
|  |  | Metric Tonnes (MT) |  |  |  |  |  |  |  |  |  |
| Domestic refrigeration (includes residential use of refrigerators and freezers) |  | 0.00 | 0.00 | 37.55 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 37.55 | 21.73% |
| Domestic Air-Conditioning/ Commercial AC | Split Non-ducted Units | 10.50 | 6.74 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 17.24 | 9.98% |
|  | Split Ducted Units | 0.00 | 4.81 | 0.00 | 0.00 | 3.82 | 8.10 | 0.00 | 0.00 | 16.73 | 9.68% |
|  | Roof Top ducted Units |  | 4.60 |  |  | 4.19 | 6.90 | 0.00 | 0.00 | 15.69 | 9.08% |
|  | Multi Split Units | 0.00 | 0.65 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.65 | 0.38% |
|  | AC Chillers | 0.00 | 2.02 | 2.04 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 4.05 | 2.34% |
| Commercial/ Industrial refrigeration | Centralized Units | 0.00 | 0.00 | 0.48 | 5.99 | 0.00 | 0.00 | 2.99 | 0.00 | 9.45 | 5.47% |
|  | Process Chillers | 0.00 | 0.00 | 2.23 | 7.44 | 0.00 | 0.00 | 3.97 | 0.00 | 13.63 | 7.89% |
|  | Stand-alone | 0.00 | 0.00 | 0.01 | 0.00 | 0.00 | 0.00 | 0.00 | 0.66 | 0.68 | 0.39% |
|  | Condensing Units | 0.00 | 0.32 | 2.73 | 4.43 | 0.00 | 0.00 | 2.73 | 6.84 | 17.06 | 9.87% |
| Marine Refrigeration | Marine Vessels | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00% |
|  | ICE Making Facilities | 0.00 | 0.00 | 0.00 | 1.15 | 0.00 | 0.00 | 1.11 | 0.00 | 2.26 | 1.31% |
| Transport Refrigeration | Refrigerated Trucks | 0.00 | 0.00 | 0.12 | 2.78 | 0.00 | 0.00 | 0.00 | 0.00 | 2.89 | 1.67% |
| Mobile AC | Large MACs | 0.00 | 0.00 | 12.89 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 12.89 | 7.46% |
|  | Small MACs | 0.00 | 0.00 | 22.05 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 22.05 | 12.76% |
| Total use (MT) |  | 10.50 | 19.15 | 80.09 | 21.78 | 8.00 | 15.00 | 10.80 | 7.50 | 172.83 | 100.00% |
|  | % Share | 6.08% | 11.08% | 46.34% | 12.60% | 4.63% | 8.68% | 6.25% | 4.34% | 100.00% |  |

Table 12:  Distribution of HFC use in RAC sub-sectors (2022)

Table 13: Distribution of HFC use for RAC sub-sectors direct emission in TCO2eq. (2022)

| Subsector |  | Refrigerants |  |  |  |  |  |  |  | Total | Share of Consumption % |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | R32 | R410A | R134a | R404A | R407C | R407A | R507A | R508B | TCO₂eq. |  |
| GWP |  | 675 | 2,088 | 1,430 | 3,922 | 1,774 | 2,107 | 3,985 | 6,808 |  |  |
|  |  | TCO2eq. |  |  |  |  |  |  |  |  |  |
| Domestic refrigeration (includes residential use of refrigerators and freezers) |  | 0.00 | 0.00 | 53,696.50 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 53,696.50 | 13.88% |
| Domestic Air-Conditioning/ Commercial AC | Split Non-ducted Units | 7,089.73 | 14,073.51 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 21,163.24 | 5.47% |
|  | Split Ducted Units | 0.00 | 10,049.02 | 0.00 | 0.00 | 6,774.57 | 17,062.43 | 0.00 | 0.00 | 33,886.03 | 8.76% |
|  | Roof Top ducted Units | 0.00 | 9,612.11 | 0.00 | 0.00 | 7,424.19 | 14,538.30 | 0.00 | 0.00 | 31,574.60 | 8.16% |
|  | Multi Split Units | 0.00 | 1,359.49 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 1,359.49 | 0.35% |
|  | AC Chillers | 0.00 | 4,210.45 | 2,910.05 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 7,120.50 | 1.84% |
| Commercial/ Industrial refrigeration | Centralized Units | 0.00 | 0.00 | 679.25 | 23,473.17 | 0.00 | 0.00 | 11,925.11 | 0.00 | 36,077.53 | 9.32% |
|  | Process Chillers | 0.00 | 0.00 | 3,189.96 | 29163.21 | 0.00 | 0.00 | 15,803.55 | 0.00 | 48,156.72 | 12.45% |
|  | Stand-alone | 0.00 | 0.00 | 19.91 | 0.00 | 0.00 | 0.00 | 0.00 | 4,502.69 | 4522.60 | 1.17% |
|  | Condensing Units | 0.00 | 676.61 | 3,902.23 | 17,391.51 | 0.00 | 0.00 | 10,874.38 | 46,560.78 | 79405.52 | 20.52% |
| Marine Refrigeration | Marine Vessels | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00% |
|  | ICE Making Facilities | 0.00 | 0.00 | 0.00 | 4,510.30 | 0.00 | 0.00 | 4,438.29 | 0.00 | 8,948.59 | 2.31% |
| Transport Refrigeration | Refrigerated Trucks | 0.00 | 0.00 | 167.09 | 10,884.17 | 0.00 | 0.00 | 0.00 | 0.00 | 11,051.26 | 2.86% |
| Mobile AC | Large MACs | 0.00 | 0.00 | 18,439.14 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 18,439.14 | 4.77% |
|  | Small MACs | 0.00 | 0.00 | 31,531.50 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 31,531.50 | 8.15% |
| Total use (MT) |  | 7,089.73 | 39,981.19 | 114,535.63 | 85,422.35 | 14,198.76 | 31,600.73 | 43,041.34 | 51,063.47 | 386,933.22 | 100% |
|  | % Share | 1.83% | 10.33% | 29.60% | 22.08% | 3.67% | 8.17% | 11.12% | 13.20% | 100% |  |

### Refrigeration servicing sector

- Domestic refrigeration

Domestic Refrigeration, from the survey definition, includes refrigeration equipment such as refrigerators, chest freezers, portable cooling systems that are found in residential households, as well as commercial office buildings, restaurants, supermarkets in the country. The stock data in 2022 for domestic refrigeration stands at 2,001,565 (shown in Table 14). The current dominant refrigerant used is R134a, followed by R600a, and R290 respectively.

Table 14: Domestic Refrigeration and Refrigerant Use

|  | Stock (2022) | % of Equipment using refrigerant |  |  |
| --- | --- | --- | --- | --- |
|  |  | R134a | R600a | R290 |
| Domestic ref | 2,001,565 | 60% | 35% | 5% |
| Refrigerant (Mt) |  | 36.99 | 21.58 | 3.08 |
| TCO2eq |  | 53,696.50 | 21.58 | 0.00 |

- Commercial refrigeration

Commercial refrigeration comprises of condensing units and standalone units which are commonly use in commercial processes. Based on the data collected as shown in Table 15, R508B and R404A are the most frequently used refrigerants in this sub-sector.

Table 15: Commercial Refrigeration and Refrigerant Use

|  | % Equipment using refrigerant |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | CONDENSING UNIT |  |  |  |  |  | STAND ALONE UNIT |  |  |  |
|  | Stock (2022) | R134a | R404A | R507A | R410A | R508B | STOCK (2022) | R134a | R600a | R508B |
|  | 122 | 16% | 26% | 16% | 1.90% | 40.10% | 9283 | 2.00% | 3.00% | 95.00% |
| Refrigerant use (MT) |  | 2.73 | 4.43 | 2.73 | 0..32 | 6.84 |  | 0.01 | 0.02 | 0.66 |
| TCO2eq |  | 3,902.23 | 17,391.51 | 10,874.38 | 676.61 | 46,560.78 |  | 19.91 | 0.02 | 4,502.69 |

- Industrial refrigeration

Industrial refrigeration comprises of centralised systems and process chillers which are commonly use in industrial processes. In Sierra Leone, the large users of industrial level manufacturing, process refrigeration in the country are the brewery and fishing related cold storages. Based on the data collected as shown in Table 16, R404A and R507A are the most frequently used refrigerants in this sub-sector.

Table 16: Industrial Refrigeration and Refrigerant Use

|  | % Equipment using refrigerant |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | PROCESS CHILLERS |  |  |  |  |  | CENTRALIZED UNIT |  |
|  | Stock (2022) | R134a | R404A | R507A | STOCK (2022) | R134a | R404A | R507A |
|  | 24 | 17.20% | 54% | 28.80% |  | 5.5% | 63% | 31.50% |
| Refrigerant use (MT) |  | 2.27 | 7.44 | 3.97 |  | 0.48 | 5.99 | 2.99 |
| TCO2eq |  | 3,386.87 | 29,163.21 | 15,803.55 |  | 1679.25 | 2,3473.17 | 11,925.11 |

- Transport refrigeration

Transport refrigeration refers to the technology used to maintain specific low temperatures in the cargo areas of trucks, vans, and trains. This is crucial for the safe transportation of perishable goods, such as food, pharmaceuticals, or other temperature-sensitive materials. From the survey, this sub-sector consumes 95% of R404A, 4% of R134a and 1% of R22 as shown in Table 17.

Table 17: Transport Refrigeration and Refrigerant Use

|  | Stock (2022) | % Equipment using refrigerant |  |  |
| --- | --- | --- | --- | --- |
|  |  | R404A | R134a | R22 |
| Transport Ref | 49 | 95% | 4% | 1% |
| Refrigerant use (MT) |  | 2.78 | 0.12 | 0.03 |
| TCO2eq |  | 10,884.17 | 167.00 | 52.87 |

- Marine refrigeration

For the survey, the marine sub-sector data provided is in relation to fishing vessels and ice making facilities. The common refrigerants use in the ice making facilities are R404A and R507A, whereas the refrigerants used by vessels are R717 and R22 (see Table 18).

Table 18: Marine Refrigeration and Refrigerant Use

|  | % Equipment using refrigerant |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
|  | ICE MAKING FACILITIES |  |  | FISHING ESSELS |  |
|  | Stock (2022) | R404A | R507A | Stock (2022) | R22 |
|  | 6 | 50.50% | 49.50% | 16 | 100% |
| Refrigerant Use (MT) |  | 1.14 | 1.11 |  | 4.80 |
| TCO2eq |  | 4,510.00 | 4,438.29 |  | 8,688.00 |

### Air conditioning servicing sector

- Domestic AC

The domestic AC sub-sector comprise of single split units that are prevalent in the country, even in large residential blocks across households, small and large commercial entities. Table 19 shows that R32 dominates the domestic AC sub-sector.

Table 19: Domestic AC and Refrigerant Use

|  | Stock (2022) | % of Equipment using refrigerant |  |  |  |
| --- | --- | --- | --- | --- | --- |
|  |  | R410A | R32 | R22 | R290 |
| split NON-DUCTED ACs | 499,088 | 27.01% | 42.09% | 16% | 15% |
| Refrigerant use (MT) |  | 6.74 | 10.50 | 3.99 | 3.74 |
| TCO2eq |  | 14,073.51 | 7,089.73 | 1,992.56 | 0.00 |

- Commercial AC

The commercial AC sub-sector refers to Multi splits, ducted splits, roof top ACs, AC chillers and centralized systems.  These systems are commonly used to cool commercial buildings, large office spaces, airports, plaza (malls), large hotels, hospitals, large supermarkets in the country. Shown in Table 20 are the refrigerant use in this sub-sector.

Table 20: Commercial AC and Refrigerant Use

|  |  | % Equipment using refrigerant |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  | MULTI-SPLIT |  |  | AC CHILLERS |  |  |  |
|  | Stock (2022) | R410A | R22 | Stock (2022) | R410A | R134a | R22 |
|  | 257 | 65% | 35% | 74 | 43.60 | 44% | 12.40% |
| Refrigerant Use (MT) |  | 0.65 | 0.35 |  | 2.02 | 2.04 | 0.57 |
| TCO2eq |  | 1,359.49 | 634.57 |  | 4,218.87 | 2,915.87 | 1,040.11 |
|  | SPLIT DUCTED |  |  |  |  |  |  |
|  | Stock (2022) | R410A | R407C | R407A |  | R22 |  |
|  | 9,300 | 23% | 18.25% | 38.70% |  | 20% |  |
| Refrigerant Use (MT) |  | 4.81 | 3.82 | 8.10 |  | 4.19 |  |
| TCO2eq |  | 10,049.02 | 6,774.57 | 17,062.43 |  | 7,574.85 |  |
| ROOF TOP DUCTED |  |  |  |  |  |  |  |
|  | Stock (2022) | R410A | R407C | R407A |  | R22 |  |
|  | 306 | 22% | 20% | 33% |  | 25% |  |
| Refrigerant Use (MT) |  | 4.60 | 4.19 | 6.91 |  | 5.23 |  |
| TCO2eq |  | 9,612.11 | 7,424.19 | 14,549.36 |  | 9,468.56 |  |

- Mobile AC

The mobile air conditioning (AC) sub-sector primarily refers to the systems that provide climate control for vehicles, including cars, SUVs, commercial trucks, buses in Sierra Leone.

Survey data conducted showed, Mobile AC systems consume 100% of R134a as shown in Table 21.

Table 21: Mobile AC Refrigeration and Refrigerant Use

|  | % Equipment using refrigerant |  |  |  |
| --- | --- | --- | --- | --- |
|  | SMALL CARS |  | LARGE CARS |  |
|  | Stock (2022) | R134a | Stock (2022) | R134a |
|  | 61,274 | 100% | 10,813 | 100% |
| Refrigerant Use (MT) |  | 22.06 |  | 12.89 |
| TCO2eq |  | 31,531.50 |  | 18,439.14 |

- Fire Suppression

From the survey, there is no evidence of HFC usage in this sector. The dominant suppression systems used are CO2 and dry powder based.

- Aerosol and Solvent

From the survey, there is no evidence of HFC usage, since all the related companies visited in this sector do not use HFC based substances in their production.

- Foam

From the survey, there is no evidence of HFC usage, since all the related companies visited in this sector do not use HFC based substances in their production.

HFC use and TCO2eq. emissions across sectors as of 2022

In summary, it is evident that Domestic refrigeration sector dominates the HFC refrigerant consumption of 37.55MT with TCO2eq. emissions estimated at 13.88%. This is largely due to the use of R134a in this sub-sector.

However, the Commercial and Industrial refrigeration with HFC consumption of about 10.26% and 13.36% has the highest corresponding TCO2eq. emissions is of 21.69% and 21.77% respectively when compared to the other RAC sub-sectors.

Figure 3: Comparison of HFC use and TCO2eq emissions across sectors as of 2022

Figure 4: Comparison of HFC use and TCO2eq emissions as of 2022

# III. HFC PHASE-DOWN STRATEGY

## III.1	Overarching strategy

Based on the experience with the HPMP it is evident that the first approach to having a sustainable transitional change in the RAC sector in Sierra Leone begins with the enabling environment that will allow for the smooth transition to zero/low GWP technologies (Stage 1). Sierra Leone aims to follow the established MP reduction targets for HFC use to define the stages of the KIP. Therefore, a total of 4 stages are planned in order to achieve the 80% HFC reduction by 2045.

Sierra Leone fully imports both refrigerants and RAC equipment and will want to use the first stage of the KIP to put in place the necessary legal regime, undertake capacity building for technicians and enforcement agencies, and also undertake stakeholder engagements to get the buy in of all major stakeholders that will ensure the smooth transition of the RAC industry to low/zero GWP refrigerants. The first stage of the KIP will also be running side by side with the countries HPMP and hence lessons learnt from the ongoing HPMP can also aid in better crafting out other stages of the KIP in future.

Also the phased approach to HFC reduction allows for new technologies especially those based on low GWP and natural refrigerants to become more accessible worldwide as well as in the country.

In order to develop any detailed strategy for KIP, it is imperative to have a reasonably good understanding of the prevailing conditions in RAC industry today and also understand the trajectory of HFC growth under Business as Usual (BAU) scenarios. These projections assist in identifying the suitable interventions that are required to be undertaken to achieve the necessary impact on the HFC use in the RAC sector.

## III.2	Projections of HFC consumption, prioritization, and proposed reductions

As the country embarks on the phase down of HFCs which stretches until 2045, it is important that along with the understanding of the current status of HFC use and existing RAC equipment stocks, the country must also be able to model how HFC use, and stocks are likely to develop under the Business as Usual (BAU) scenario.

In order to have a realistic projection for HFC consumption, the data collected for the KIP provided the needed information to have the current distribution of HFC use in all the RAC sub-sectors. This data was then models side by side with the past HFC consumption and this provided the right trend lines that was used to estimate to estimate HFC use into the future.

The dataset, from the KIP HFC survey, also provided insight into some strategies for prioritizing actions associated with HFC consumption. It emphasized the significance of identifying sectors, applications, or regions where HFC emissions had a notable environmental impact. We employed a prioritization framework to channel efforts and resources toward areas with the highest potential for reducing emissions.

This provides a comprehensive presentation of proposed reductions in HFC consumption. These reduction strategies were meticulously analysed and aligned with international agreements like the Kigali Amendment. The detailed phased approach to reductions, specifying timelines and targets for curbing HFC emissions.

HFC use expected to grow under BAU

In this section, a comprehensive analysis of refrigerant usage was undertaken, focusing specifically on the expected growth in Hydrofluorocarbon (HFC) utilization under the Business-as-Usual (BAU) scenario.

The data presented in Figure 5 sheds light on the trends, variations, and implications of HFC usage across various sectors and applications, offering valuable insights into the environmental impact of unchecked HFC consumption.

Figure 5: HFC use expected to grow under BAU expected to grow under BAU

The analysis examined the consumption patterns of several key refrigerants, shedding light on their individual trajectories over the years.

- R507A: Consumption of R507A remained relatively low and stable for several years before a gradual increase from 2020 onwards. This suggests its continued use in applications where alternatives may not yet be fully adopted.

- R410A: R410A remained relatively low and stable for several years before a gradual increase from 2021 onwards. This suggests its continued use in applications where alternatives may not yet be fully adopted

- R134a: This refrigerant experienced steady growth from 2016. R-134A was commonly used in automotive air conditioning systems, and its decline may be linked to regulatory transitions towards more climate-friendly alternatives.

- R32: The consumption of R32 started in 2022, then it started growing from 2023. Its adoption might be driven by its lower global warming potential (GWP) compared to some other HFCs, making it a preferable choice for various applications.

- R404A: R404A consumption exhibited notable fluctuations over the years. It saw a peak in 2021 and then underwent periodic declines and rebounds. The varying usage may `reflect the challenges in transitioning away from high-GWP refrigerants in certain applications.

- R407A and R407C: These refrigerants displayed usage patterns characterized by modest consumption levels, with minor fluctuations. Their usage could be associated with specific niche applications or regions with differing regulatory landscapes.

- R508B: Consumption of R508B remained relatively low for several years before a gradual increase from 2020 onwards. This suggests its continued use in applications where alternatives may not yet be fully adopted.

III.3 Comparison between HFC consumption under BAU and Kigali phase down Schedule

The analysis reveals a substantial contrast between Hydrofluorocarbon (HFC) consumption under Business-as-Usual (BAU) conditions and the phase-down schedule outlined in the Kigali Amendment. This contrast is particularly evident due to the significant increase in HFC usage projected under BAU, in comparison to the controlled reduction proposed by the Kigali Amendment.

This situation requires drastic measures to bring down HFC usage within acceptable levels in order to achieve the targets proposed by the Kigali Amendment. Under the BAU scenario presented in Figure 6, HFC consumption experiences consistent growth, resulting in a substantial increase in the utilization of these compounds. By 2050, HFC consumption is projected to reach 1,189,030.33 TCO2 equivalent (CO2eq).

The Kigali Amendment provides a structured approach to reduce HFC consumption. This international agreement aims to curtail the production and usage of HFCs to mitigate their adverse environmental impact. The Kigali Amendment establishes a cap for HFC consumption at 351,294.00 TCO2eq by 2024 but HFC consumption is expected to decrease to 245,906.00 TCO2eq by 2036, while the BAU projection for the same year stands at 678,287.34 TCO2eq. By 2050, the Kigali Amendment envisions a further reduction in HFC consumption to 70,259.00 TCO2eq, in contrast to the BAU projection of 1,189,030.33 TCO2eq.

Figure 6: Comparison between HFC consumption under BAU and Kigali phase down Schedule

Below are the estimated emissions from the use of HFC in the RAC sector under BAU conditions. Table 22 shows that it is expected that the freeze of 2024 can be met by Sierra Leoneunder BAU scenerio however the 10% reduction in 2029 might not be met under BAU scenerio. The KIP strategy aims to address this difference to ensure compliance is achieved while coordinating with ongoing HCFC phase out activities.

| HFC emissions (BAU) TCO2eq |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | 2020 | 2021 | 2022 | 2023 | 2024 | 2025 | 2026 | 2027 | 2028 | 2029 |
| HFC consumption | 250,390 | 307,211 | 386,932 | 402,761 | 419,237 | 436,388 | 454,240 | 472,823 | 492,166 | 512,300 |
| Annual increase (%) in HFC consumption |  | 22.69 | 25.95 | 4.09 | 4.09 | 4.09 | 4.09 | 4.09 | 4.09 | 4.09 |
| MLF Compliance target (TCO2eq) |  |  |  |  | 351,294 |  |  |  |  | 316,165 |
| Reduction required (TCO2eq) |  |  |  |  |  |  |  |  |  | 196,135 |

Table 22:  Total HFC emissions projections under BAU Scenario

## III.4	Detailed KIP strategy

Stage I (2024-2029)

The KIP Stage I strategy will specifically target the enabling environment to facilitate the freeze on growth of HFC refrigerant in the country and allow for overall 10% reduction. It will target to do this through legislation and operation of an industry wide quota system and vetting new construction application where low GWP technologies will be recommended for adoption (see Table 23).

The following are the planned activities:

- Regulatory frameworks: Putting in the necessary controls to ban and reduce the importation of high GWP gasses and equipment for which there are already low GWP technology alternatives. This target will be on domestic refrigerators, commercial standalone units, single split and multi-split air conditioners. Legislation will also be put in place to also prevent the potential use of HFC’s in other non-RAC sectors such as fire suppression, foam and painting sectors.

Legislation will also be put in place to compel commercial and industrial RAC operators to have adequately sized in-house recovery equipment to minimise their purchase of HFCs.

Putting in place measures to promote sustainable refrigeration practices and procedures in the RAC sector to reduce leakage.

- Demo project: Undertake at least one demonstration project using low GWP technology in the commercial refrigeration sector.

- Capacity building: Developing and implementing targeted training program for RAC technicians, customs and enforcement officers and other professionals. This will include updating the training curricula of the Sierra Leone Technical Institute. The focus of the Technicians training will be for MAC technicians in the leak-proofing, containment and effective recovery of R-134a. The focus for the Customs and other enforcement agencies training will be in line with HFC and other low GWP refrigerants.

- Recovery, recycling and reclaiming: Legislation to compel commercial and industrial RAC operators to have adequately sized in-house recovery equipment to minimise their purchase of HFCs. Also, supporting MAC garages (support 6 garages) with MAC servicing tools and training of technicians. EPA will license these selected garages as "Green MAC garages", this will also advertise them for more patronage of customers.

Stage II (2030-2035) will focus on the enabling environment to transition the MAC and commercial/industrial refrigeration and commercial air conditioning sectors to low/zero technologies sector and other complimentary activities.

Stage III (2035-2040) will focus on the full transition of the MAC, commercial / industrial refrigeration and commercial air conditioning to low/ ZERO GWP technologies as well as other complimentary activities.

Stage IV (2040-2045) will continue stage III activities and achieve 100% conversion within the domestic, commercial, industrial refrigeration and air conditioning sector. It is hoped that by then low/zero GWP refrigerants will be more globally available, and locally, to consolidate the gains made.

Table 23: Planned Stages of the KIP and potential activities

| OVERALL STRATEGY |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Stages (years) | Reduction target | Substance | Sector | Focus activities | Cross cutting |
| Stage I (2`024 - 2029) | 10% | R134a, R410A, R404A, HFC227ea | Main focus - Industrial Ref. - MAC - Fire suppressant Other: - Dom Ref. - Small commercial - Dom AC | - Regulatory frameworks – Putting in the necessary controls to ban and reduce the importation of high GWP gasses and equipment for which there are already low GWP technology alternatives. This target will be on domestic refrigerators, commercial standalone units, single split and multi-split air conditioners. Legislation will also be put in place to also prevent the potential use of HFC’s in other non-RAC sectors such as fire suppression, foam and painting sectors. - Legislation will also be put in place to compel commercial and industrial RAC operators to have adequately sized in-house recovery equipment to minimise their purchase of HFCs. - Putting in place measures to promote sustainable refrigeration practices and procedures in the RAC sector to reduce leakage. - Demo project - Undertake at least one demonstration project using low GWP technology in the commercial refrigeration sector. - Capacity building - Developing and implementing targeted training program for RAC technicians, customs and enforcement officers and other professionals. This will include updating the training curricula of the Sierra Leone Technical Institute. The focus of the Technicians training will be for MAC technicians in the leak-proofing, containment and effective recovery of R-134a. The focus for the Customs and other enforcement agencies training will be in line with HFC and other low GWP refrigerants) - Recovery, recycling and reclaiming: Legislation to compel commercial and industrial RAC operators to have adequately sized in-house recovery equipment to minimise their purchase of HFCs. - An assessment of MAC garages will be done and a number of them will be selected to be used as MAC garages of excellence. These workshops will be assessed on some key provisions in their garages such as good workmanship, provision of right MAC servicing tools, qualification of MAC technicians etc. The NOU will have an MOU with these garages to be used as Training workshops in leak proofing and containment of refrigerants in the MAC sub-sector. The workshops will be given some financial tokens to them for their assistance. Also these MAC Centres of Excellence can be used in future for any Demonstration project in the MAC sub-sector As a benefit to the garages they will be designated by the EPA/NOU as MAC Garages of Excellence. This recognition will showcase these garages as good MAC servicing workshops and encourage persons with MAC servicing need to contact them for support, thereby increasing their revenue. They will also become exemplary workshops that other workshops can emulate to also rise to become MAC Centres of Excellence. | Capacity building Gender Mainstreaming Awareness |
| Stage II (2030 – 2035) | 30% | R134a, R410A, R407c, R507A, HFC227ea | - Com Ref. - Com AC - MAC - Fire suppressant | - Will focus on the enabling environment to transition the MAC and commercial/industrial refrigeration and commercial air conditioning sectors to low/zero technologies sector and other complimentary activities. | Capacity building Gender Mainstreaming Awareness |
| Stage III (2036 - 2040) | 50% | R134a, R410A, R404A, R407C, R32 | - Com Ref. - Com AC | - Will focus on the full transition of the MAC, commercial / industrial refrigeration and commercial air conditioning to low/ZERO GWP technologies as well as other complimentary activities. | Capacity building Gender Mainstreaming Awareness |
| Stage IV (2040 - 2045) | 80% | R134a, R410A, R404A, R407C, R32 | - Com Ref. - Com AC - Transport Ref. - Dom AC - Dom Ref. | - Will continue stage III activities and achieve 100% conversion within the domestic, commercial, industrial refrigeration and air conditioning sector. It is hoped that by then low/zero GWP refrigerants will be more globally available, and locally, to consolidate the gains made. | Capacity building Gender Mainstreaming Awareness |

## III.5	Stage I implementation programme

### Activities to be implemented under KIP Stage I

One of the main overall strategy is to ensure the full transition of the domestic refrigeration and air conditioning sub-sectors to low/zero GWP refrigerants, and also demonstrate the adoption of low GWP in the commercial refrigeration sector.

Other aims of the first stage of the KIP is to be put in the right enabling environment that will push other RAC sub-sectors, which are still in their nurturing stages to adopt to low/zero GP refrigerants, to at least recover and reuse HFCs used. This will be on the MAC and commercial/ industrial refrigeration sub-sectors.

The activities for Sierra Leone is to be implemented under six (6) components, namely;

- Component 1: Legal and regulatory measures to support HFC phase down

- Component 2: Enforcement of HFC controls

- Component 3: Capacity building

- Component 4: Demonstration of pilot projects on commercial refrigeration sector

- Component 5: Other gender mainstreaming

- Component 6: Monitoring

While establishing new goals, the actions that fall under the six (6) previously stated components of the overall plan are made to guarantee that stage II of the HPMP's activity continues. The suggested activities and work plan schedule for the first stage of the HFC phase-down plan are summarized and their projected costs are shown in Table 24 and Table 25 respectively.

Table 24:  KIP Stage I Tranches and budget for proposed activities

| Activities proposed (2024-2029) |  | Other Sub- Sector | Other Details | Activity Cost (US$) |  | Tranches (US$) |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  | UNEP | UNIDO | Tranche 1 | Tranche 2 | Tranche 3 | Total Cost (US$) |
| 1. Legal & regulatory measures to support HFC phase down |  |  |  |  |  |  |  |  |  |
| 1.1 | Coordinate with EC and other relevant key stakeholder’s whiles banning HCFC based equipment to include the ban of RAC equipment using HFC refrigerants with high GWP in the domestic ref., and commercial standalone ref units to HC refrigerants by January 2025. | All Sectors | Seed money of $10,000 will be used to support this activity; assist with meetings and fees to redraft the legislation. | 0.00 | 10,000.00 | 4,000.00 | 3,000.00 | 3,000.00 | 10,000.00 |
| 1.2 | Support the NOU to establish a national HFC quota system and framework including criteria for quota allocation with provisions for enforcement and monitoring. | All Sectors | The $3,000 funding will be used for periodic stakeholder engagement to monitor and address concerns in the use of the quota system. | 3,000.00 | 0.00 | 3,000.00 | 0.00 | 0.00 | 3,000.00 |
| 1.3 | Legislation to compel commercial and industrial RAC operators to have adequately sized in-house recovery equipment to minimise their purchase of HFCs. | Industrial/ Commercial Ref. | Seed money of $2,550 will be used to support this activity; legislation to compel commercial and industrial RAC operators to have adequately sized in-house recovery equipment to minimise their purchase of HFCs. | 0.00 | 2,550.00 | 2,550.00 | 0.00 | 0.00 | 2,550.00 |
| 1.4 | Development of a National Cooling Plan: A clear guiding document that will guide the Country to plan, prepare and move along with low GWP and natural refrigerants. In Africa successive administrations tend to take different strategic paths once in office. Thus a comprehensive National Plan that will assist any successive administration understand the current and future Cooling path of the country is very paramount. This plan will cover all the varying cooling sectors and help frame a “Cooling Policy” for all the RAC sub-sectors that will ensure low GWP, and natural refrigerants are adopted and up scaled in the country. The national cooling plan will bring out financial and technical gaps (limitations) of both the HPMP and KIP so that any future cooling activities to be proposed for the country can be used to undertake these gaps. These gaps can be rebate schemes and some expensive demonstration projects that can help to transform the market. | All Sectors | Appointment of international consultant is pegged at $ 5,500 (i.e. $250 per day for specialist for 22 working days) for the revised National Cooling Plan (NCP). Also, appointment of local consultant is pegged at $ 6,600 (i.e. $300 per day for specialist for 22 working days) for the revised National Cooling Plan (NCP). A key stakeholder’s workshop engagement to review and validate the revised National Cooling Plan (NCP) is pegged at $2,500 (i.e. $50 per person for 50 people for stipend and food. Also $300 for conference room rent). | 14,900.00 | 0.00 | 0.00 | 14,900.00 | 0.00 | 14,900.00 |
| 1.5 | Revise ODS regulation to include high GWP HFC refrigerant such as R23 by Jan. 2025. Also allow for the ban of R410A and R404 by 2029. Also, revise Ozone Depleting and other Chemical Regulations to include the ban on HFC chemical in the Fire suppression, foam, aerosols and solvents sectors in the country by January 2026: The survey established that there is no use of HFC in the country excluding the RAC sector. However, it is important to put in the right legislations to prevent any possible import of any HFC based chemicals, for the fire suppression, foam, aerosols and solvents sectors, since they are still globally available. The legislation will clearly spell out that only natural refrigerants or chemicals with no ODS/ GWP can be imported and used. | All Sectors | Appointment of local consultant is pegged at $ 6,600 (i.e. $300 per day for specialist for 22 working days) for the revised ODS and other chemical regulation to ban HFC use in Fire suppression, foam, solvent and aerosol. A key stakeholder’s workshop engagement to review and validate the revised ODS and other chemical regulation is pegged at $750 (i.e. $50 per person for 15 people for stipend and food. Also $300 for conference room rent). | 7,650.00 | 0.00 | 7,650.00 | 0.00 | 0.00 | 7,650.00 |
| 1.6 | Revise Building codes, MEPS and labels for RAC units: a. Building codes will be revised to mention the use of low GWP refrigerants and other technologies that promote the use of relatively less refrigerants such as water chilled systems for buildings. Low GWP refrigerants that will be promoted will be hydrocarbons, HFO’s and to the extreme R32. This will be by 2025. b. MEPS will also be revised to mention the kind of Refrigerant that can be used apart from the energy efficiency level. The GWP of Affordable low GWP refrigerants will be proposed as a benchmark to make it affordable for end-users. This will be by 2025. | All Sectors | Appointment of international consultant is pegged at $ 5,500 (i.e. $250 per day for specialist for 22 working days) for the revised Building codes, MEPs and Labels for RAC units. Also, appointment of local consultant is pegged at $ 6,600 (i.e. $300 per day for specialist for 22 working days) for the revised Building codes, MEPs and Labels for RAC units. A key stakeholder’s workshop engagement to review and validate the revised Building codes, MEPs and Labels for RAC units is pegged at $2,500 (i.e. $50 per person for 50 people for stipend and food. Also $300 for conference room rent). | 14,900.00 | 0.00 | 14,900.00 | 0.00 | 0.00 | 14,900.00 |
|  | Sub total |  |  | 40,450.00 | 12,550.00 | 32,100.00 | 17,900.00 | 3,000.00 | 53,000.00 |
| 2. Enforcement of HFC controls |  |  |  |  |  |  |  |  |  |
| 2.1 | Revise and upgrade customs training curriculum to include HFCs, HCs, natural refrigerants, new HS code etc. | All Sectors | Appointment of local consultant is pegged at $ 8,800 (i.e. $400 per day for specialist for 22 working days) for the revised custom training curriculum. A key stakeholder’s workshop engagement to review and validate the revised custom training curriculum is pegged at $1,200 (i.e. $50 per person for 20 people for stipend and food. Also $300 for conference room rent). | 10,100.00 | 0.00 | 10,100.00 | 0.00 | 0.00 | 10,100.00 |
| 2.2 | TOT for customs officers on New revised curriculum (10 custom officers). | All Sectors | For 5 Males and 5 Females. Training per person (theory, practical and other miscellaneous) is pegged at $ 500 for 2 tranches (i.e. $50 per person for 10 people for stipend and food). | 1,000.00 | 0.00 | 0.00 | 500.00 | 500.00 | 1,000.00 |
| 2.3 | Organizing workshops and training for clearing agents on the new revised curriculum. | All Sectors | Workshop for 50 clearing agents is pegged at $ 50 per person for 2 tranches (i.e. for food and stipend). | 5,000.00 | 0.00 | 2,500.00 | 2,500.00 | 0.00 | 5,000.00 |
|  | Sub total |  |  | 16,100.00 | 0.00 | 12,600.00 | 3,000.00 | 500.00 | 16,100.00 |
| 3. Capacity building |  |  |  |  |  |  |  |  |  |
| 3.1 | Upgrade training curricula for RAC vocational/technical instructions to include HFCs HCs and natural refrigerants | All Sectors | Appointment of international consultant is pegged at $ 8,800 (i.e. $400 per day for specialist for 22 working days) for the revised draft Legislative regime on the ban of HFC based equipment. A key stakeholder’s workshop engagement to review and validate the revised Legislative regime is pegged at $1,700 (i.e. $50 per person for 30 people for stipend and food. Also $300 for conference room rent). | 10,600.00 | 0.00 | 10,600.00 | 0.00 | 0.00 | 10,600.00 |
| 3.2 | Develop a CO2 training programme at the centre of excellence training centre. | Commercial /Industrial Ref. | Appointment of international consultant is pegged at $ 8,800 (i.e. $400 per day for specialist for 22 working days) for the revised draft Legislative regime on the ban of HFC based equipment. A key stakeholder’s workshop engagement to review and validate the revised Legislative regime is pegged at $1,700 (i.e. $50 per person for 30 people for stipend and food. Also $300 for conference room rent). | 10,600.00 | 0.00 | 10,600.00 | 0.00 | 0.00 | 10,600.00 |
| 3.3 | Awareness creation on HFCs, HCs, natural refrigerants and Kigali Implementation plan (KIP) among RAC importers, distributors and retailers of refrigerant and equipment’s. | All Sectors | Workshop for 50 importers, distributors and retailers (refrigerants and equipment’s) is pegged at $ 50 per person (i.e. for food, stipend). Also, $300 is for conference room rent. | 2,800.00 | 0.00 | 1,400.00 | 1,400.00 | 0.00 | 2,800.00 |
| 3.4 | Awareness creation for Built Environment professionals and procurement officers on HFCs, HCs, natural refrigerants, design, specify and procure of RAC Units for end-users. | All Sectors | Workshop for 50 built environment professionals and procurement officers is pegged at $ 50 per person (i.e. for food and stipend). Also, $300 is for conference room rent. | 2,800.00 | 0.00 | 1,400.00 | 0.00 | 1,400.00 | 2,800.00 |
| 3.5 | Stakeholder’s engagement with Vehicle importers to frame a National Policy for the Mobile AC sector to shift from use of R134a to HFO’s or any globally acceptable natural refrigerant for vehicle air conditioning. | Mobile AC | Workshop for 20 major Vehicle importers is pegged at $ 50 per person (i.e. for food and stipend). Also, $300 is for conference room rent. | 1,300.00 | 0.00 | 1,300.00 | 0.00 | 0.00 | 1,300.00 |
| 3.6 | License of selected MAC garages (support 6 garages) to become MAC centre of excellence by EPA/NOU. | Mobile AC | License 2 MAC garages each at the north belt, middle belt and southern belt of the country. This is pegged at $6,200 | 0.00 | 6,200.00 | 6,200.00 | 0.00 | 0.00 | 6,200.00 |
|  | Subtotal |  |  | 28,100.00 | 6,200.00 | 31,500.00 | 1,400.00 | 1,400.00 | 34,300.00 |
| 4. Demonstration of pilot projects on commercial refrigeration sector |  |  |  |  |  |  |  |  |  |
| 4.1 | Demonstration project for R290 monoblocks for +ve/-ve temps. Size (1/3- 2.5HP) installation, commissioning and training at the centre of excellence. | Commercial Ref. | Demonstration of R290 monoblocks installation system is pegged at $46,000 | 0.00 | 46,000.00 | 0.00 | 46,000.00 | 0.00 | 46,000.00 |
|  | Subtotal |  |  | 0.00 | 46000.00 | 0.00 | 46000.00 | 0.00 | 46000.00 |
| 5. Other gender mainstreaming |  |  |  |  |  |  |  |  |  |
| 5.1 | Awareness creation on the RAC industry for junior level students (50% male, 50% females). | All Sectors | Awareness creation for 100 junior level female student on the RAC industry is pegged at $ 30 per person (i.e. for food, water, drink souvenirs and transport). Also, $300 is for Venue related expenses. | 6,600.00 | 0.00 | 3,300.00 | 0.00 | 3,300.00 | 6,600.00 |
| 5.2 | Encouraging women role models presentation in all KIP Implementation workshop. | All Sectors | The presentation of women role models in all KIP Implementation workshop is pegged at $ 6,000 (i.e. accommodation, transport, food and stipend). | 6,000.00 | 0.00 | 2,000.00 | 2,000.00 | 2,000.00 | 6,000.00 |
|  | Subtotal |  |  | 12,600.00 | 0.00 | 5,300.00 | 2,000.00 | 5,300.00 | 12,600.00 |
| 6. Monitoring |  |  |  |  |  |  |  |  |  |
| 6.1 | Project Monitoring Unit (PMU) support and coordination. | All Sectors | The project coordination is pegged at 18,000 for the proposed KIP Stage I activities (i.e. 10% of the project amount). | 12,600.00 | 5,400.00 | 7,000.00 | 6,000.00 | 5,000.00 | 18,000.00 |
|  | Subtotal |  |  | 12,600.00 | 5,400.00 | 7,000.00 | 6,000.00 | 5,000.00 | 18,000.00 |
|  | TOTAL |  |  | 109,850.00 | 70,150.00 | 88,500.00 | 76,300.00 | 15,200.00 | 180,000.00 |

| Activities proposed (2024-2029) |  | Year |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | 2024 | 2025 | 2026 | 2027 | 2028 | 2029 |
| 1. Legal & regulatory measures to support HFC phase down |  |  |  |  |  |  |  |  |
| 1.1 | Coordinate with EC and other relevant key stakeholder’s whiles banning HCFC based equipment to include the ban of RAC equipment using HFC refrigerants with high GWP in the domestic ref., and commercial standalone ref units to HC refrigerants by January 2025. |  | X |  | X |  | X |  |
| 1.2 | Support the NOU to establish a national HFC quota system and framework including criteria for quota allocation with provisions for enforcement and monitoring. |  | X |  | X |  | X |  |
| 1.3 | Legislation to compel commercial and industrial RAC operators to have adequately sized in-house recovery equipment to minimise their purchase of HFCs. |  | X |  |  |  |  |  |
| 1.4 | Development of a National Cooling Plan: |  |  | X |  |  |  |  |
| 1.5 | Revise ODS regulation to include high GWP HFC refrigerant such as R23 by Jan. 2025. Also allow for the ban of R410A and R404A by 2029. Also revise Ozone Depleting and other Chemical Regulations to include the ban on HFC chemical in the Fire suppression, foam, aerosols and solvents sectors in the country by January 2026. |  |  | X |  |  |  |  |
| 1.6 | Revise Building codes, MEPS and labels for RAC units. |  |  | X |  |  |  |  |
| 2. Enforcement of HFC controls |  |  |  |  |  |  |  |  |
| 2.1 | Revise and upgrade customs training curriculum to include HFCs, HCs, natural refrigerants, new HS code etc. |  |  | X |  |  |  |  |
| 2.2 | TOT for customs officers on New revised curriculum (10 custom officers). |  |  |  |  | X |  | X |
| 2.3 | Organizing workshops and training for clearing agents on the new revised curriculum. |  | X |  |  | X |  |  |
| 3. Capacity building |  |  |  |  |  |  |  |  |
| 3.1 | Upgrade training curricula for RAC vocational/technical institutions to include HFCs HCs and natural refrigerants. |  |  | X |  |  |  |  |
| 3.2 | Develop a CO2 training programme at the centre of excellence training centre. |  |  |  |  | X |  |  |
| 3.3 | Awareness creation on HFCs, HCs, natural refrigerants and Kigali Implementation plan (KIP) among RAC importers, distributors and retailers of refrigerant and equipment’s. |  | X |  |  | X |  |  |
| 3.4 | Awareness creation for Built Environment professionals and procurement officers on HFCs, HCs, natural refrigerants, design, specify and procure of RAC Units for end-users. |  | X |  |  | X |  |  |
| 3.5 | Stakeholder’s engagement with Vehicle importers to frame a National Policy for the Mobile AC sector to shift from use of R134a to HFO’s or any globally acceptable natural refrigerant for vehicle air conditioning. |  | X |  |  |  |  |  |
| 3.6 | License of selected MAC garages (support 6 garages) to become MAC centre of excellence by EPA/NOU. |  |  | X |  |  |  |  |
| 4. Demonstration of pilot projects on commercial refrigeration sector |  |  |  |  |  |  |  |  |
| 4.1 | Demonstration project for 2 pilots R290 monoblocks for +ve/-ve temps. Size (1/3- 2.5HP) installation, commissioning and training at the centre of excellence |  |  |  |  | X | X |  |
| 5. Other gender mainstreaming |  |  |  |  |  |  |  |  |
| 5.1 | Awareness creation on the RAC industry for junior level students (50% male, 50% females) |  |  |  |  | X |  | X |
| 5.2 | Encouraging women role models presentation in all w KIP Implementation workshop. |  | X |  | X |  | X |  |
| 7. Monitoring |  |  |  |  |  |  |  |  |
| 7.1 | Project Monitoring Unit (PMU) support and coordination. |  | X | X | X | X | X | X |

Table 25: Work plan schedule for proposed activities for KIP Stage I

## III.6	Relation between the Kigali HFC implementation plan and the HCFC phase-out management plan

Sierra Leone has just started implementation of the Stage II HPMP which aims to bring about the complete phase out of HCFC use by 2030. However, Sierra Leone is well placed to coordinate the activities of the HPMP Stage II and the KIP Stage I as both UNIDO and UNEP are implementing the HPMP and now the KIP.  With this continuation of the implementing agencies, we will ensure that all parties are well informed about the ongoing activities in the HPMP and how these can be used to amplify the planned actions with respect to the KIP and prevent duplication of efforts.

The synergy between the HPMP Stage II and the KIP Stage I is shown in Table 26.

Table 26: Synergy between the HPMP Stage II and the KIP Stage I

| HPMP Stage II |  | KIP Stage I |
| --- | --- | --- |
| 1. Establishment of the regulatory environment |  | 1. Establishing & implementing regulatory framework |
| Engage a National expert to develop the national technical standards in the RAC sector |  | Coordinate with EC and other relevant key stakeholder’s whiles banning HCFC based equipment to include the ban of RAC equipment using HFC refrigerants with high GWP in the domestic ref., and commercial standalone ref units to HC refrigerants by January 2025. |
| Stakeholders’ consultation (workshops) to review the draft standards prepared by the National expert |  | Support the NOU to establish a national HFC quota system and framework including criteria for quota allocation with provisions for enforcement and monitoring. |
| Training of Trainers by national expert (UNEP) |  | Development of a National Cooling Plan: |
| Facilitate border dialogues |  | Revise ODS regulation to include high GWP HFC refrigerant such as R23 by Jan. 2025. Also allow for the ban of R410A and R404A by 2029. |
| Review of customs training curriculum (UNEP) |  | Also revise Ozone Depleting and other Chemical Regulations to include the ban on HFC chemical in the Fire suppression, foam, aerosols and solvents sectors in the country by January 2026. |
| Conducting training workshops for customs officers and other law enforcement agencies (UNEP |  | Revise Building codes, MEPS and labels for RAC units. |
|  |  | Legislation to compel commercial and industrial RAC operators to have adequately sized in-house recovery equipment to minimise their purchase of HFCs. |
| 2. Focused awareness-raising/capacity-building of target groups |  | 2. Enforcement of HFC controls |
| Publication and printing of the relevant standards and its dissemination(Conduct capacity building training for the procurement officers to promote procurement of environmentally friendly technologies, and facilitate development of policies to support procurement of green RAC systems) |  | Revise and upgrade customs training curriculum to include HFCs, HCs, natural refrigerants, new HS code etc. |
| Training session to build the capacity of standards officers, environmental officers and other key stakeholders for the development and enforcement of technical standards in the RAC sector |  | TOT for customs officers on New revised curriculum (10 custom officers). |
| Conduct monitoring inspection on imported RAC equipment and refrigerants to ensure compliance with the technical standards |  | Organizing workshops and training for clearing agents on the new revised curriculum. |
| A training workshop for procurement officers on procurement of “green” RAC systems (2 training workshops) |  |  |
| Sensitize the general public on benefits of adopting and using green RAC systems |  |  |
| 3. Training and certification of technicians in RAC servicing |  | 3. Capacity building |
| Engage an expert to facilitate the strengthening of certification scheme for the RAC servicing sector |  | Upgrade training curricula for RAC vocational/technical institutions to include HFCs HCs and natural refrigerants |
| Conduct stakeholder consultations on formulation of an effective RAC certification scheme |  | Develop a CO2 training programme at the centre of excellence training centre. |
| Build capacity of key stakeholders involved in the certification process |  | Awareness creation on HFCs, HCs, natural refrigerants and Kigali Implementation plan (KIP) among RAC importers, distributors and retailers of refrigerant and equipment’s. |
| Update national codes of conduct for RAC servicing technicians and revision of the National RAC training curriculum (national expert will be recruited) |  | Awareness creation for Built Environment professionals and procurement officers on HFCs, HCs, natural refrigerants, design, specify and procure of RAC Units for end-users. |
| Conduct 10 training sessions for RAC technicians on good servicing practices |  | Stakeholder’s engagement with Vehicle importers to frame a National Policy for the Mobile AC sector to shift from use of R134a to HFO’s or any globally acceptable natural refrigerant for vehicle air conditioning. |
| Strengthening of the RAC association and RAC training institutes provision of tool kits |  | License of selected MAC garages (support 6 garages) to become MAC centre of excellence by EPA/NOU |
| 4. Recovery, recycling and training programme |  |  |
| Establishment of refrigerant recovery and re-use scheme, including set up of one reclaim centre |  |  |
| 5. Facilitating the adoption of R-290 technology and environmentally sound alternative technologies |  | 5. Demonstration of pilot projects on commercial refrigeration sector |
| Strengthening the three centres of excellence through provision of toolkits and upgrade tools for hydrocarbons handling, additional identifiers |  | Demonstration project for 2 pilots R290 monoblocks for +ve/-ve temps. Size (1/3- 2.5HP) installation, commissioning and training at the centre of excellence. |
| Technical assistance to promote R290 uptake in the country: assessment of operation and awareness raising program. |  |  |
| Certified trainer program for hydrocarbon-based equipment |  |  |
| 6. Gender mainstreaming |  | 6. Gender mainstreaming |
| The NOU like all Other Institution has incorporated issues of gender mainstreaming into it activities and programs. More particularly , the NOU is enforcing as a key Government Directives the idea of 30% inclusion of Female in its activities and programs like trainings , workshop etc. In addition, the NOU has included specialized, trainings of FEMALE RAC Technicians into its annual activities and also provided budgetary line for equipment. Also NOU provides has made free of cost the License and certification scheme for all Female RAC technicians and disable technicians |  | Awareness creation on the RAC industry for junior level female students. 50% males and 50% females. |
|  |  | Encouraging women role models presentation in all KIP Implementation workshop. |
| 7. Project Management |  | 7. Project monitoring |
| Project coordination, monitoring, evaluation and reporting for KIP. |  | Project Monitoring Unit (PMU) support and coordination for HPMP |

III.7	Other impacts on the environment including the climate

The proposed activities and their potential impact to the environment is discussed in Table 27.

Table 27: proposed activities and their potential impact to the environment

| Proposed KIP Stage 1 Activity | Other details |
| --- | --- |
| Ban of HFC based refrigerators | Minimise use of R134a |
| Ban of HFC based standalone commercial units | Minimise use of R134a, |
| Ban use of R410A to R32 in single and multi-split unit to R-32 | Minimise use of R410A |
| Minimise leakages, and recover and reuse HFC in the MAC sub-sector | Minimise use of R134a |
| Minimise leakages, recover and reuse HFC in the Industrial/ Commercial sub-sector | Minimise use of R404A |

III.8	Sustainability and risk assessment

Sierra Leone has made great progress on enforcing controls and meeting the KIP phase-down objectives for HFCs by implementing a strong regulatory framework. Many facets of civilization depend on cooling, therefore any interruption to its function might have dire repercussions. Sierra Leone must choose appropriate replacement technologies while lowering its HCFC use in order to accomplish a smooth transition. Putting HPMP into practice is essential to achieving KIP goals. The evaluation of risks and sustainability are essential elements of this endeavour.

Balancing Technology Choice: The availability of alternative refrigerants, such as natural refrigerants or HFCs, in Sierra Leone will depend on a number of factors, including pricing, expertise, and skills, as well as the availability of technology. The focused strategy of the HPMP, in conjunction with financing efforts, is intended to tackle the particular issues encountered by the R22 domestic split AC industry. Sierra Leone hopes to avoid an exponential rise in HFC use by being aware of HFC phase down regulations and making investments in reclamation, certification, and training.

Integration with HPMP and Government Efforts: The government's initiatives and continuing work under the HPMP are strongly correlated with Sierra Leone's KIP plan. The goal is to reduce indirect emissions from obsolete and inefficient RAC equipment and shift the cooling industry to more ecologically friendly refrigerants. To guarantee a long-term, steady decrease in greenhouse gas emissions, Sierra Leone has implemented MEPS and restrictions on used equipment. Furthermore, tighter regulations on equipment using high greenhouse gas (GHG) refrigerants and HFC equipment will support overall sustainability initiatives.

Capacity Building for a Sustainable Future: The KIP places a strong emphasis on increasing capacity in the MAC and commercial refrigeration industries. By means of demonstration and instruction in the utilization of novel technologies, like R290 monoblocks, local training institutions, technicians, and companies may become acquainted with these eco-friendly substitutes. As HFC phase-down objectives tighten, this knowledge transfer will help with the adoption of these technologies and ensure the long-term sustainability of skills and expertise in the nation.

The Table 28 attempts to identify and categorize risks based on current understanding of the situation in the country.

Table 28:  Potential risks and mitigation measurers

| Risk | Mitigation | Level of Risk |
| --- | --- | --- |
| Delayed implementation of the quota system for HFCs | The country cannot achieve its 2024 freeze target without applying a quota system. Therefore, a quota system must be applied to ensure compliance is achieved by 2029. | High |
| Supply chain constraint limiting availability of low GWP technologies in the local market | As the project progresses through demonstrations, it is important that the supply chain for these newly developed technologies is improved and that initial domestic importer buy-in is facilitated through external support to ensure successful market transition. | High |
| High influx of HFC based RAC equipment into the country | Revising the MEPS for domestic AC and domestic refrigeration and developing of MEPS for the other sub sectors to curtail the use of HFC based equipment. | High |
| BAU compliance will increase the consumption of HFC use | HFC's BAU growth forecast, and associated estimates of compliance reduction requirements are based on the best available data and an understanding of local conditions. In cases where HFC consumption exceeds the expected instrumental quantity, i.e. the equipment import quota, financial measures may also be applied to prevent non-compliance. | High |
| Increased demand in domestic AC | These systems currently operate with high GWP refrigerants, use large quantities, and frequently leak. The project should encourage a ban on the use of R410A and the use of HFC 32 or any low or zero GWP refrigerant. Containment should also be a key component of HPMPS/KIPS training, which can limit refrigerant loss. | Medium |

III.9	Consideration of the Multilateral Fund gender mainstreaming policy

The Government of Sierra Leone is fully aware that Gender mainstreaming is integral to its national development plan by adopting a National Gender Policy that seeks to empower women to participate and benefit from all national development strides.

The Policy seeks to institutionalize the political, economic, and social rights of women by creating an appropriate structure in government offices and institutions so that the public policies and interventions are gender-sensitive and can ensure equitable development for all Sierra Leone men and women.

In line with the Ex Com decision 84/92, as well as, UNEP and UNIDO gender mainstreaming policies, KIP Stage I implementation will take care of the gender equality and women’s empowerment, from the project board and project management team to consultants, and from training to active participation in consultation workshops.

During the implementation of KIP Stage I, NOU will aim to seek stakeholders’ inputs on how to integrate gender specific indicators in planning, implementation, and reporting process of each component.

A focus will be encouraged to support gender balanced participation in training and capacity building activities and benefit from other supporting measures.

Links with the government agencies, the private sector, Non-governmental organisations, community-based organizations, and women’s associations or groups whose work focuses on gender mainstreaming  and the specific area of intervention will be utilized to mainstream country specific gender sensitive actions to mirror project’s components and to both strengthen and benefit from national expertise.

The meetings and trainings will aim to incorporate sessions on gender to further sensitize participants on the importance of gender mainstreaming and women empowerment. Communication and awareness activities will be targeted to this end as well as aim women as a specific audience group.

Table 29:  Gender mainstreaming

| Project component | Question | Answer |  |  |
| --- | --- | --- | --- | --- |
|  |  | Yes | No | Partially |
| Project preparation | Does the project concept include consideration of the different situations of women and men and of the impact the project will have on these different societal groups? | X |  |  |
|  | Does the project explicitly address one or more of the identified gender issues/gender-differentiated project impacts? Please describe how, and if not provide an explanation. | X |  |  |
| Data and statistics | Where applicable, does the project require the collection of sex-disaggregated data and qualitative information to analyse and track gender issues? | X |  |  |
| Results framework | Are outcomes, output and activities designed to meet the different needs and priorities of women and men? |  |  | X |
|  | Does the results framework include gender-responsive indicators, targets and baseline data to monitor gender equality results? |  |  | X |
| Budget | Has the budget taken into account allocations for the proposed gender activities (e.g., capacity-building activities for female technicians)? | X |  |  |
| Stakeholders and participation | Are women/gender-focused Ministries, groups, associations or gender units in partner organizations consulted/included in the project? |  |  | X |
|  | Does the project ensure that both women and men can provide input, access, and participate in project activities (e.g., through outreach/inviting female technicians to participate in capacity-building activities)? | X |  |  |
| Gender capacities | Has a gender expert been recruited or does project staff have gender knowledge and gender-related tasks incorporated into their job descriptions? |  |  | X |
|  | Will project staff and stakeholders be sensitized to gender (e.g., through completion of UN Women online training courses)? | X |  |  |
| Implementation arrangement | Is there gender-balanced recruitment of project personnel and gender-balanced representation in project boards and steering committees? |  |  | X |
| Monitoring and evaluation | Does the monitoring and evaluation component of the project require specific reporting on gender issues and on progress made to address them, both quantitatively and qualitatively? | X |  |  |

III.10	Co-financing

The primary aim of all co-financing efforts within the KIP in the country is to extend the impact of limited funding available but also foster collaboration and shared responsibility among stakeholders by encouraging supported contributions from various stakeholders. Building upon existing initiatives under the HPMP, the KIP will continue and expand co-financing measures to maintain continuity of actions and achieve its objectives. Several key co-financing measures will be implemented as part of the KIP:

Training Institutes Collaboration: Institutes involved with the MAC Centre of Excellence will sign Memorandums of Understanding (MOUs) with the NOU. These MOUs will allow the usage of their facilities at little or no cost for trainings conducted by the NOU. This collaboration will foster knowledge-sharing and skill development within the industry.

Demonstration Projects: In the case of demonstration projects, beneficiaries will be made to support the necessary building plumbing, electrical and civil works. An MOU will be signed between the NOU and the beneficiary, outlining these contributions to ensure successful implementation of the demonstration projects.

Awareness Raising Activities: Existing websites, social media platforms, forums, and newsletters of both government and private stakeholders will be utilized to spread information about the KIP activities, goals, and initiatives. This comprehensive dissemination strategy will ensure a wider reach of the KIP message through multiple channels. Additionally, the NOU will be invited to present the KIP at all relevant forums, both government and private, across the country, enabling uniform knowledge sharing and reducing the need for formal advertising costs.

MAC Garages and Technicians Contribution: An assessment of MAC garages will be done and a number of them will be selected to be used as MAC garages of excellence. These workshops will be assessed on some key provisions in their garages such as good workmanship, provision of right MAC servicing tools, qualification of MAC technicians etc.

The NOU will have an MOU with these garages to be used as Training workshops in leak proofing and containment of refrigerants in the MAC sub-sector. The workshops will be given some financial tokens to them for their assistance. Also these MAC Centres of Excellence can be used in future for any Demonstration project in the MAC sub-sector

As a benefit to the garages they will be designated by the EPA/NOU as MAC Garages of Excellence. This recognition will showcase these garages as good MAC servicing workshops and encourage persons with MAC servicing need to contact them for support, thereby increasing their revenue. They will also become exemplary workshops that other workshops can emulate to also rise to become MAC Centres of Excellence.

III.11	Business plan

Considering that the approved cost guidelines for the phase-down of HFC in Article 5 countries have been recently released, UNEP did not include the HFC phase-down plan for Sierra Leone in its recent business plans (see Table 30).

Table 30: Business plan

| BUSINESS PLAN ALLOCATION AND FUNDING |  |  |  |  |
| --- | --- | --- | --- | --- |
| Funding (US $) | 2024-25 | 2026-27 | 2028-30 | Total |
| Business plan allocation |  |  |  |  |
| Proposed amount | 88,500.00 | 76,300.00 | 15,200.00 | 180,000 |
|  |  |  |  | Yes/No/n.a. |
| Justification provided if KIP funding is not included in the business plan |  |  |  | Yes |
| Justification provided if KIP value varies from the proposed amount of funding |  |  |  | N/A |
| Funding consistent with HFC phase-down cost guidelines regarding the cut-off date, second stage conversions, and cost-effectiveness thresholds (indicate “n.a.” if the guidelines are not approved yet) |  |  |  | Yes |
| Funding for the last tranche requested in the last year of implementation |  |  |  | No |
| Justification provided on how the proposed funding levels can enable the fulfilment of the required disbursement threshold by the time of the next tranche request |  |  |  | Yes |
| Consideration of policies on individual projects in determining funding levels, i.e., transnational corporations, foreign ownership, unintentional technology upgrade, public domain technologies, incremental operating savings (e.g., alternative energy savings) |  |  |  | Yes |

IV. PROJECT COORDINATION AND MANAGEMENT

The projection coordination and the management team for the HPMP Stage II will be the same team to handle the Kigali Implementation Plan (KIP) monitoring implementation activities. Thus, the Environment Protection Agency through the Environmental Health and Safety National Ozone Unit is responsible for the implementation of the KIP in Sierra Leone. The National Ozone Unit established within the Chemicals Control and Management will coordinate and oversee the implementation of KIP programmes and activities. Relevant Institutions will also be involved in the implementation of the KIP activities, these institutions are but not limited to the following: NOU, National Chemicals Management e Committee, Chambers of Commerce, Ministry of Finance, Ministry of Trade and Industry, National Revenue Authority Customs Department, and other enforcement bodies and the RAC Technicians.

The responsibility of the NOU will be to ensure effective communications between the partners and monitoring of progress towards achievement of expected results. The National Ozone Unit under the Environment protection Agency is the national lead agency that will coordinate the implementation of the project.

The National Chemicals Management Committee is an advisory body to the NOU. The committee comprises key stakeholders involved in the ODS phase out activities which include representatives of government Ministries, Agencies and Departments, private sectors, NGOs and civil society. The committee will be the ultimate decision maker on implementation of the project. It will ensure that the KIP Stage I project remains on course to deliver the desired outcomes. It will review and approve Annual Work Plans (AWP) and annual progress achieved by the project based on the approved AWPs. It will further be responsible for reviewing and approving annual import quotas of HFCs. The committee will meet on a quarterly basis and prior to the quarterly meetings; the NOU will duly submit the progress report on the previous period and the plan for the next quarter.

The Chambers of Commerce of Sierra Leone will play a key role in the implementation of KIP Stage I project. They will play a key role in dissemination of information to the RAC industry, importers and the public to enhance successful phase-out of HCFCs and increased adoption of low GWP energy efficiency technologies. It will be working closely with the NOU and enforcement bodies to make sure that policies and standards in the RAC sector are effectively enforced.

The National Revenue Authority Customs Department is the key enforcement agency of regulations on the management of controlled substances under the KIP. The department will continue to enforce the control measures on imports and exports of HFCs and other controlled substances under the KIP. Customs Department in collaboration with the NOU and other relevant enforcement agencies will continue to monitor implementation of the licensing and quota systems to ensure sustainable transitioning from use of HFCs to low GWP alternative technologies.

V. PLAN OF ACTION FOR THE FIRST TRANCHE

Table 31: First Tranche Plan of Action

| Activities proposed (2024-2026) |  | Other Sub- Sector | Other Details | Activity Cost (US$) |  | Tranches (US$) |
| --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  | UNEP | UNIDO | Tranche 1 |
| 1. Legal & regulatory measures to support HFC phase down |  |  |  |  |  |  |
| 1.1 | Coordinate with EC and other relevant key stakeholder’s whiles banning HCFC based equipment to include the ban of RAC equipment using HFC refrigerants with high GWP in the domestic ref., and commercial standalone ref units to HC refrigerants by January 2025. | All Sectors | Seed money of $4,000 will be used to support this activity; assist with meetings and fees to redraft the legislation. | 0.00 | 4,000.00 | 4,000.00 |
| 1.2 | Support the NOU to establish a national HFC quota system and framework including criteria for quota allocation with provisions for enforcement and monitoring. | All Sectors | The $3,000 funding will be used for periodic stakeholder engagement to monitor and address concerns in the use of the quota system. | 3,000.00 | 0.00 | 3,000.00 |
| 1.3 | Legislation to compel commercial and industrial RAC operators to have adequately sized in-house recovery equipment to minimise their purchase of HFCs. | Industrial/ Commercial Ref. | Seed money of $2,550 will be used to support this activity; legislation to compel commercial and industrial RAC operators to have adequately sized in-house recovery equipment to minimise their purchase of HFCs. | 0.00 | 2,550.00 | 2,550.00 |
| 1.4 | Revise ODS regulation to include high GWP HFC refrigerant such as R23 by Jan. 2025. Also allow for the ban of R410A and R404 by 2029. Also, revise Ozone Depleting and other Chemical Regulations to include the ban on HFC chemical in the Fire suppression, foam, aerosols and solvents sectors in the country by January 2026: The survey established that there is no use of HFC in the country excluding the RAC sector. However, it is important to put in the right legislations to prevent any possible import of any HFC based chemicals, for the fire suppression, foam, aerosols and solvents sectors, since they are still globally available. The legislation will clearly spell out that only natural refrigerants or chemicals with no ODS/ GWP can be imported and used. | All Sectors | Appointment of local consultant is pegged at $ 6,600 (i.e. $300 per day for specialist for 22 working days) for the revised ODS and other chemical regulation to ban HFC use in Fire suppression, foam, solvent and aerosol. A key stakeholder’s workshop engagement to review and validate the revised ODS and other chemical regulation is pegged at $750 (i.e. $50 per person for 15 people for stipend and food. Also $300 for conference room rent). | 7,650.00 | 0.00 | 7,650.00 |
| 1.5 | Revise Building codes, MEPS and labels for RAC units: a. Building codes will be revised to mention the use of low GWP refrigerants and other technologies that promote the use of relatively less refrigerants such as water chilled systems for buildings. Low GWP refrigerants that will be promoted will be hydrocarbons, HFO’s and to the extreme R32. This will be by 2025. b. MEPS will also be revised to mention the kind of Refrigerant that can be used apart from the energy efficiency level. The GWP of Affordable low GWP refrigerants will be proposed as a benchmark to make it affordable for end-users. This will be by 2025. | All Sectors | Appointment of international consultant is pegged at $ 5,500 (i.e. $250 per day for specialist for 22 working days) for the revised Building codes, MEPs and Labels for RAC units. Also, appointment of local consultant is pegged at $ 6,600 (i.e. $300 per day for specialist for 22 working days) for the revised Building codes, MEPs and Labels for RAC units. A key stakeholder’s workshop engagement to review and validate the revised Building codes, MEPs and Labels for RAC units is pegged at $2,500 (i.e. $50 per person for 50 people for stipend and food. Also $300 for conference room rent). | 14,900.00 | 0.00 | 14,900.00 |
|  | Sub total |  |  | 25,550.00 | 6,550.00 | 32,100.00 |
| 2. Enforcement of HFC controls |  |  |  |  |  |  |
| 2.1 | Revise and upgrade customs training curriculum to include HFCs, HCs, natural refrigerants, new HS code etc. | All Sectors | Appointment of local consultant is pegged at $ 8,800 (i.e. $400 per day for specialist for 22 working days) for the revised custom training curriculum. A key stakeholder’s workshop engagement to review and validate the revised custom training curriculum is pegged at $1,200 (i.e. $50 per person for 20 people for stipend and food. Also $300 for conference room rent). | 10,100.00 | 0.00 | 10,100.00 |
| 2.2 | Organizing workshops and training for clearing agents on the new revised curriculum. | All Sectors | Workshop for 25 clearing agents is pegged at $ 50 per person for 1st tranche (i.e. for food and stipend). | 2,500.00 | 0.00 | 2,500.00 |
|  | Sub total |  |  | 12,600.00 | 0.00 | 12,600.00 |
| 3. Capacity building |  |  |  |  |  |  |
| 3.1 | Upgrade training curricula for RAC vocational/technical instructions to include HFCs HCs and natural refrigerants. | All Sectors | Appointment of international consultant is pegged at $ 8,800 (i.e. $400 per day for specialist for 22 working days) for the revised draft Legislative regime on the ban of HFC based equipment. A key stakeholder’s workshop engagement to review and validate the revised Legislative regime is pegged at $1,700 (i.e. $50 per person for 30 people for stipend and food. Also $300 for conference room rent). | 10,600.00 | 0.00 | 10,600.00 |
| 3.2 | Develop a CO2 training programme at the centre of excellence training centre. | Commercial /Industrial Ref. | Appointment of international consultant is pegged at $ 8,800 (i.e. $400 per day for specialist for 22 working days) for the revised draft Legislative regime on the ban of HFC based equipment. A key stakeholder’s workshop engagement to review and validate the revised Legislative regime is pegged at $1,700 (i.e. $50 per person for 30 people for stipend and food. Also $300 for conference room rent). | 10,600.00 | 0.00 | 10,600.00 |
| 3.3 | Awareness creation on HFCs, HCs, natural refrigerants and Kigali Implementation plan (KIP) among RAC importers, distributors and retailers of refrigerant and equipment’s. | All Sectors | Workshop for 25 importers, distributors and retailers (refrigerants and equipment’s) is pegged at $ 50 per person (i.e. for food, stipend). Also, $150 is for conference room rent. | 1,400.00 | 0.00 | 1,400.00 |
| 3.4 | Awareness creation for Built Environment professionals and procurement officers on HFCs, HCs, natural refrigerants, design, specify and procure of RAC Units for end-users. | All Sectors | Workshop for 25 built environment professionals and procurement officers is pegged at $ 50 per person (i.e. for food and stipend). Also, $150 is for conference room rent. | 1,400 | 0.00 | 1,400.00 |
| 3.5 | Stakeholder’s engagement with Vehicle importers to frame a National Policy for the Mobile AC sector to shift from use of R134a to HFO’s or any globally acceptable natural refrigerant for vehicle air conditioning. | Mobile AC | Workshop for 20 major Vehicle importers is pegged at $ 50 per person (i.e. for food and stipend). Also, $300 is for conference room rent. | 1,300.00 | 0.00 | 1,300.00 |
| 3.6 | License of selected MAC garages (support 6 garages) to become MAC centre of excellence by EPA/NOU | Mobile AC | License 2 MAC garages each at the north belt, middle belt and southern belt of the country. This is pegged at $6,200 | 0.00 | 6,200.00 | 6,200.00 |
|  | Subtotal |  |  | 25,300.00 | 6,200.00 | 31,500.00 |
| 4. Other gender mainstreaming |  |  |  |  |  |  |
| 4.1 | Awareness creation on the RAC industry for junior level students (50% male, 50% females) | All Sectors | Awareness creation for 50 junior level female student on the RAC industry is pegged at $ 30 per person (i.e. for food, water, drink souvenirs and transport). Also, $150 is for Venue related expenses. | 3,300.00 | 0.00 | 3,300.00 |
| 4.2 | Encouraging women role models presentation in all KIP Implementation workshop. | All Sectors | The presentation of women role models in all KIP Implementation workshop is pegged at $ 2,000 (i.e. accommodation, transport, food and stipend). | 2,000.00 | 0.00 | 2,000.00 |
|  | Subtotal |  |  | 5,300.00 | 0.00 | 5,300.00 |
| 5. Monitoring |  |  |  |  |  |  |
| 5.1 | Project Monitoring Unit (PMU) support and coordination | All Sectors | The project coordination is pegged at 7,000 for the proposed KIP Stage I activities (i.e. 10% of the project amount). | 4,000.00 | 3,000.00 | 7,000.00 |
|  | Subtotal |  |  | 4,000.00 | 3,000.00 | 7,000.00 |
|  | TOTAL |  |  | 72,750.00 | 15,750.00 | 88,500.00 |

# ANNEX: AGREEMENT BETWEEN THE GOVERNMENT AND THE EXERCUTIVE COMMITTEE

## Appendix A: TEMPLATE SCHEDULE OF PHASE-DOWN COMMITMENTS AND FUNDING TRANCHES UNDER THE KIP

| Row | Particulars | 2023 | 2024 | 2025 | 2026 | 2027 | 2028 | 2029 | Total |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1.1 | Montreal Protocol reduction schedule of Annex F substances (CO2-eq tonnes)* |  | 351,294 | 351,294 | 351,294 | 351,294 | 351,294 | 316,165 | n/a |
| 1.2 | Maximum allowable total consumption of Annex F substances (CO2-eq tonnes)* |  | 351,294 | 351,294 | 351,294 | 351,294 | 351,294 | 316,165 | n/a |
| 2.1 | Lead IA UNIDO agreed funding (US $) |  | 43,809 |  | 34,073 |  | 19,470 |  | 97,351 |
| 2.2 | Support costs for Lead IA (US $) |  | 4,381 |  | 3,407 |  | 1,947 |  | 9,735 |
| 2.3 | Cooperating IA UNEP agreed funding (US $) |  | 29,093 |  | 22,627 |  | 12,930 |  | 64,650 |
| 2.4 | Support costs for Cooperating IA (US $) |  | 3,782 |  | 2,942 |  | 1,552 |  | 8,275 |
| 3.1 | Total agreed funding (US $) |  | 72,900 |  | 56,700 |  | 32,400 |  | 162,000 |
| 3.2 | Total support costs (US $) |  | 8,160 |  | 6,346 |  | 3,494 |  | 18,000 |
| 3.3 | Total agreed costs (US $) |  | 81,064 |  | 63,048 |  | 35,899 |  | 180,000 |

*Estimated values to be revised once the HFC baseline is established

## Appendix B: SCHEDULE OF PHASE-OUT COMMITMENTS AND FUNDING TRANCHES UNDER THE HPMP

| (VI) PROJECT DATA |  |  | 2021 | 2022 | 2023 | 2024 | 2025 | 2026 | 2027-2029 | 2030 | Total |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Montreal Protocol consumption limits |  |  | 1.10 | 1.10 | 1.10 | 1.10 | 0.55 | 0.55 | 0.55 | 0 | n/a |
| Maximum allowable consumption (ODP tonnes) |  |  | 0.56 | 0.56 | 0.56 | 0.56 | 0.26 | 0.26 | 0.26 | 0 | n/a |
| Projects costs requested in principle (US $) | UNEP | Project costs | 135,000 | 0 | 90,000 | 0 | 0 | 70,000 | 0 | 58,000 | 353,000 |
|  |  | Support costs | 17,550 | 0 | 11,700 | 0 | 0 | 9,100 | 0 | 7,540 | 45,890 |
|  | UNIDO | Project costs | 117,000 | 0 | 70,000 | 0 | 0 | 0 | 0 | 0 | 187,000 |
|  |  | Support costs | 10,530 | 0 | 6,300 | 0 | 0 | 0 | 0 | 0 | 16,830 |
| Total project costs requested in principle (US $) |  |  | 252,000 | 0 | 160,000 | 0 | 0 | 70,000 | 0 | 58,000 | 540,000 |
| Total support costs requested in principle (US $) |  |  | 28,080 | 0 | 18,000 | 0 | 0 | 9,100 | 0 | 7,540 | 62,720 |
| Total funds requested in principle (US $) |  |  | 280,080 | 0 | 178,000 | 0 | 0 | 79,100 | 0 | 65,540 | 602,720 |

## Appendix C: SAMPLE QUESTIONNAIRE

i. End-user

ii. Sale and Import

Appendix D: SUMMARY OF EXISTING REGULATORY FRAMEWORK

| TYPE OF ACTION / LEGISLATION |  | Exist (YES/NO/PLAN) | Since when (Date) | If yes, provide brief about the legislative requirements | If No, provide comment and if/when expected |
| --- | --- | --- | --- | --- | --- |
| OVERVIEW OF HCFC RELATED POLICY OPTIONS |  |  |  |  |  |
| 1 | Establishing general guidelines to control import, production, and export of HCFCs | Yes | 2010 | The guidelines is embedded into the regulations that provide application checklist, who should apply and where to store and under what conditions |  |
| 1.1 | Regulatory procedures for HCFC data collection and reporting in place | Yes | 2010 | The National Revenue Authority should provide the relevant import/export data on ODS and refrigerant-depending equipment |  |
| 1.2 | Registration of HCFC importers/exporters | Yes | 2010 | The regulation stipulate that all import/exporter must register with NOU in the Environment Protection Agency |  |
| 1.3 | A shared database on import quotas and actual imports/exports between ozone office and customs | No |  |  |  |
| 1.4 | Mandatory reporting by HCFC importers/exporters | Yes | EPA Act 2008 Part V and EPA act 2022 Part VI ( Available on Line) | The Legislation requires all importer/ exporter of HCFCs to report on all their activities |  |
| 2 | Banning/restricting import or placing on the market of bulk quantities of: |  |  |  |  |
| 2.1 | HCFC-141b (pure substance and in mixtures) | Yes | EPA Act 2008 amended 2010 and the ODS Regulation 2010 | As provided for in the Prohibition Of Ozone Regulation 2010 there is a restriction on the import of HCFC 141b. Hence , such importation follows strictly the quota system like in the case of R-22 |  |
| 2.2 | HCFC-22 (for certain applications or total ban) | Yes | EPA Act 2008 amended 2010 and the ODS Regulation 2010 | As provided for in the Prohibition Of Ozone Regulation 2010 there is a restriction on the import of HCFC 141b. Hence , such importation follows strictly the quota system like in the case of R-23 |  |
| 3 | Banning/restricting import or placing on the market of equipment/products using high-GWP HFCs and HFC blends | The regulation do not ban or restrict import or placing on the market of equipment / product s using high- GWP HFCs and HFCs blends |  |  |  |
| 3.1 | Residential air conditioners | No |  |  |  |
| 3.2 | Commercial/Industrial refrigeration units/application (Cold Chain) | No |  |  |  |
| 3.3 | Commercial A/C (chillers, packaged units, central units) | No |  |  |  |
| 3.4 | Refrigerated trucks, marine vessels and off-shore fishing equipment | No |  |  |  |
| 3.5 | Used products/equipment containing any HCFC or HCFC blends | No |  |  |  |
| 3.6 | Use of HCFC or HCFC Blends in production of some or all types of foam | No |  |  |  |
| 3.7 | Use of HCFC or HCFC Blends as solvent | No |  |  |  |
| 4 | Record keeping |  |  |  |  |
| 4.1 | Mandatory HCFC logbooks | There is a provision within the ODS Regulation 2010 for record Keeping HCFC Logbooks and Equipment Logbooks | It is mandatory for keeping records and reporting annually on HCFC equipment and HCFC logbooks Section 8 (sub section 11) |  |  |
| 4.2 | Mandatory HCFC equipment logbooks | There is a provision within the ODS Regulation 2010 for record Keeping HCFC Logbooks and Equipment Logbooks | It is mandatory for keeping records and reporting annually on HCFC equipment and HCFC logbooks Section 8 (sub section 11) |  |  |
| 5 | Training and certification programmes |  |  |  |  |
| 5.1 | Legislative basis for training of customs officers | YES | 2008 and 2010 | The EPA Act 2008 and 2022 Part VII and the Prohibition of the ODS regulation 2010 |  |
| 5.2 | Legislative basis for training of refrigeration service technicians on HCFCs | YES | 2008 and 2010 |  |  |
| 5.3 | Legislative basis for certification of refrigeration service technicians | YES | 2008 and 2010 |  |  |
| 5.4 | Legislative basis for system for monitoring and evaluation of training programmes | YES | 2008 and 2010 | The EPA Act 2022 Part VII and the Prohibition of the ODS regulation 2010 ( Attached is the soft copy of the EPA Act 2022 and ODS Regulation 2010 |  |
| 6 | Preventing HCFC emissions |  |  |  |  |
| 6.1 | Mandatory recovery and recycling of HCFCs during equipment maintenance | No |  |  |  |
| 6.2 | Monitoring system for reporting on recovered and recycled HCFCs | No |  |  |  |
| 6.3 | Ban on venting of HCFCs | No |  |  |  |
| 6.4 | Mandatory leak checks for large capacity equipment | No |  |  |  |
| 6.5 | Mandatory recovery of refrigerants from the equipment at the end-of-life | No |  |  |  |
| 7 | Other policies |  |  |  |  |
| 7.1 | Fiscal incentive/disincentive (Tax subsidies) | No |  |  |  |
| 7.2 | Labelling of HCFC cylinders and containers | No |  |  |  |
| 7.3 | Ban on non-refillable HCFC containers | No |  |  |  |
| 7.4 | Penalties for not conforming to Regulations | Yes | There are Penalties in the ODS regulation 2010 for defaulter |  |  |
|  | OVERVIEW OF HFC RELATED POLICY OPTIONS |  |  |  |  |
| 1 | Establishing general guidelines to control import, production, and export of HFCs |  |  |  |  |
| 1.1 | HFC import/export licensing system in place for import of bulk HFCs | No |  |  |  |
| 1.2 | Regulatory procedures for HFC data collection and reporting in place | No |  |  |  |
| 1.3 | Requiring permits for import/export or sale of bulk HFCs | No |  |  |  |
| 1.4 | Quota system in place for import of HFCs (in tons of CO2 equivalent) | No |  |  |  |
| 1.5 | Registration of HFC importers/exporters | No |  |  |  |
| 1.6 | A shared database on import quotas and actual imports/exports between ozone office and customs or other relevant agencies | No |  |  |  |
| 1.7 | Mandatory reporting by HFC importers/exporters | No |  |  |  |
| 2 | Banning/restricting import or placing on the market of bulk quantities of: |  |  |  |  |
| 2.1 | High GWP HFCs | No |  |  |  |
| 3 | Banning/restricting import or placing on the market of equipment/products using high-GWP HFCs and HFC blends |  |  |  |  |
| 3.1 | Domestic refrigerators/freezers/coolers | No |  |  |  |
| 3.2 | Residential air conditioners | No |  |  |  |
| 3.3 | MAC systems | No |  |  |  |
| 3.4 | Commercial refrigeration units/application (Cold Chain) | No |  |  |  |
| 3.5 | Industrial refrigeration units/application (Cold Chain) | Noh |  |  |  |
| 3.6 | Commercial A/C (chillers, packaged units, central units) | No |  |  |  |
| 3.7 | Refrigerated trucks, marine vessels and off-shore fishing equipment | No |  |  |  |
| 3.8 | Used products/equipment containing any HFC or HFC blends | No |  |  |  |
| 3.9 | Use of HFC or HFC Blends in production of some or all types of foam | No |  |  |  |
| 3.1 | Use of HFC or HFC Blends as solvent | No |  |  |  |
| 3.11 | Use of HFC or HFC Blends for firefighting | No |  |  |  |
| 4 | Record keeping |  |  |  |  |
| 4.1 | Mandatory HFC logbooks | No |  |  |  |
| 4.2 | Mandatory HFC equipment logbooks | No |  |  |  |
| 5 | Training and certification programmes |  |  |  |  |
| 5.1 | Legislative basis for training of customs officers | YES | As provided for in the Prohibition of ODS Regulation and the EPA Act of 2022 it is a requirement for customs and other law enforcement officers to be trained regularly on the provisions of the Montreal protocol |  |  |
| 5.2 | Legislative basis for training of refrigeration service technicians on HFCs | YES | As provided for in the Prohibition of ODS Regulation and the EPA Act of 2022 it is a requirement for customs and other law enforcement officers to be trained regularly on the provisions of the Montreal protocol |  |  |
| 5.3 | Legislative basis for training of refrigeration service technicians in alternative technologies (with safety, toxicity and high-pressure considerations) | YES | As provided for in the Prohibition of ODS Regulation and the EPA Act of 2022 it is a requirement for customs and other law enforcement officers to be trained regularly on the provisions of the Montreal protocol |  |  |
| 5.4 | Legislative basis for certification of refrigeration service technicians | YES | As provided for in the Prohibition of ODS Regulation and the EPA Act of 2022 it is a requirement for customs and other law enforcement officers to be trained regularly on the provisions of the Montreal protocol |  |  |
| 5.5 | Legislative basis for system for monitoring and evaluation of training programmes | YES | As provided for in the Prohibition of ODS Regulation and the EPA Act of 2022 it is a requirement for customs and other law enforcement officers to be trained regularly on the provisions of the Montreal protocol |  |  |
| 6 | Preventing HFC emissions |  |  |  |  |
| 6.1 | Mandatory recovery and recycling of HFCs during equipment maintenance | No |  |  |  |
| 6.2 | Monitoring system for reporting on recovered and recycled HFCs | No |  |  |  |
| 6.3 | Ban on venting of HFCs | No |  |  |  |
| 6.4 | Mandatory leak checks for large capacity equipment | No |  |  |  |
| 6.5 | Mandatory recovery of refrigerants from the equipment at the end-of-life | No |  |  |  |
| 7 | Other regulations |  |  |  |  |
| 7.1 | Fiscal incentive/disincentive (Tax subsidies) | No |  |  |  |
| 7.2 | Labelling of HFC cylinders and containers | No |  |  |  |
| 7.3 | Ban on non-refillable HFC containers | No |  |  |  |
| 7.4 | Penalties for not conforming to Regulations | No |  |  |  |
|  | Other regulations, (please specify - Environment, Chemicals, Firefighting, Public Procurement, Consumer Protection, Labour, Gender, etc.) | YES | The EPA Act of 2022 encourage incentive for proponents who are taking actions to minimize impact on the environment of which the control of consumption of ODSs are part of such compliance benefits |  |  |